## How to use
Unnamed: 0 | Cortex Cloud upgrade: field assessment tracker
What this tracker answers for each account
1) Which technical blockers the customer has confirmed. 2) Which of those have no committed release date. 3) Which release clears the account, and the expected start date.
How to fill it in
1. Accounts tab: one row per account. Fill the white columns. Set Assessment status to Complete only when every relevant gap has been validated with the customer.
2. Blocker log tab: one row per gap discussed with the customer. Pick the account and gap from the dropdowns; release, default view and PM owner fill in automatically.
3. Set Customer outcome: Hard blocker, Workaround accepted, Not needed or Unknown. For a blocker that is not on the gap list, pick 'Other (not on gap list)' and describe it.
4. Record whether telemetry matched what the customer told you. These corrections improve telemetry for the next wave of accounts.
5. Playbook feedback tab: anything we should change in the runbook, telemetry or product.
How the readiness bucket is set (automatic)
Ready now: no validated hard blockers. Otherwise the latest planned release among the account's hard blockers sets the bucket.
No date: at least one hard blocker has No date, TBC, Not planned or Unknown. These rows show Escalate = Yes in the Blocker log; raise them with the PM owner.
'Oct 2026 to Jan 2027' (custom rule translation) counts as January, to plan on the later date. Apr and Jul 2027 both count as 'After April release or later'.
The bucket only shows once Assessment status is Complete. Set Expected start date yourself after agreeing it with the customer.
Legend
White cells: inputs. Grey cells: formulas, do not type over them. Grey italic rows: an example account to show the format; delete before use.
The full approach is in the TSE Field Assessment Guide.

## Summary
Field assessment summary | Unnamed: 1 | Unnamed: 2 | Unnamed: 3
All figures update from the Accounts and Blocker log tabs. Grey cells are formulas; do not type over them.
Coverage
Accounts in scope | 1
Assessments complete | 0
% complete | 0
Readiness buckets (completed assessments)
Bucket | #A | A( | %OC
Ready now | 0 | 0 | 0
After October release | 0 | 0 | 0
After January release | 0 | 0 | 0
After April release or later | 0 | 0 | 0
No date | 0 | 0 | 0
Assessment pending | 1 | 5
Blockers
Validated hard blockers (all accounts) | 1
Hard blockers with no committed date | 0
Accounts with a no-date hard blocker | 0
Workarounds accepted | 1
Blockers not on the gap list | 0
Telemetry mismatches found | 1
Most common hard blockers: sort the Gap reference tab by its last column.

## Accounts
Account iD | Account | Tier | Region | Upgrade status | ARR ($M) | TSE | Companion (ride-along) | Assessment status | Assessment date | # gaps validated | # hard blockers | # hard blockers with no date | Latest release rank | Readiness bucket | Expected start date | Next step | Escalation reason | Notes
0 | STC | Tier 1 | AMER | Upgrade in progress | 7032960 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | CTSC | Tier 1 | AMER | Upgrade in progress | 3387281 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | FM | Tier 1 | AMER | Upgrade in progress | 107136 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | MI | Tier 1 | AMER | Upgrade in progress | 2191200 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | IL | Tier 1 | JAPAC | Upgrade in progress | 59568 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | AEC | Tier 1 | AMER | Upgrade in progress | 1872802 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | SGI | Tier 1 | AMER | Upgrade in progress | 1751558 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | I | Tier 1 | JAPAC | Upgrade in progress | 1669027 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | ZFGA | Tier 1 | AMER | Upgrade in progress | 1609632 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | FNFI | Tier 1 | AMER | Upgrade in progress | 1483675 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | TNOGI | Tier 1 | AMER | Upgrade in progress | 1247274 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | NNA | Tier 1 | EMEA | Upgrade in progress | 1131332 |  |  | Sales Indicated Churn |  | 0 | 0 | 0 | 0 | Assessment pending
0 | DBSL | Tier 1 | AMER | Upgrade in progress | 773 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | WL | Tier 1 | JAPAC | Upgrade in progress | 1081949 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | LI | Tier 1 | AMER | Upgrade in progress | 1008784 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | E | Tier 1 | EMEA | Upgrade in progress | 1602702 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | AL | Tier 1 | AMER | Upgrade in progress | 807369 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | A1 | Tier 1 | EMEA | Upgrade in progress | 467026 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | LUC | Tier 1 | JAPAC | Upgrade in progress | 755874 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | OSPL | Tier 1 | JAPAC | Upgrade in progress | 325882 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | TCC | Tier 1 | AMER | Upgrade in progress | 735868 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | AGOL | Tier 1 | EMEA | Upgrade in progress | 684959 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | SBGL | Tier 1 | EMEA | Upgrade in progress | 651248 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | PSSSS | Tier 1 | LATAM | Upgrade in progress | 785724 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | MTI | Tier 2 | AMER | Upgrade in progress | 667543 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | USC&FI | Tier 2 | AMER | Upgrade in progress | 638281 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | NTI | Tier 2 | AMER | Upgrade in progress | 591945 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | L | Tier 2 | EMEA | Upgrade in progress | 556043 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | VH | Tier 2 | AMER | Upgrade in progress | 414399 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | TNS | Tier 2 | LATAM | Upgrade in progress | 521948 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | ALS | Tier 2 | EMEA | Upgrade in progress | 221649 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | DDAS | Tier 2 | LATAM | Upgrade in progress | 216512 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | BS | Tier 2 | LATAM | Upgrade in progress | 338356 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | EI | Tier 2 | AMER | Upgrade in progress | 63515 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | NLIAANZL | Tier 2 | JAPAC | Upgrade in progress | 214458 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | IL&S | Tier 2 | AMER | Upgrade in progress | 376301 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | MMCL | Tier 2 | JAPAC | Upgrade in progress | 223538 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | AGP | Tier 2 | EMEA | Upgrade in progress | 432295 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | EG | Tier 2 | EMEA | Upgrade in progress | 227991 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | F | Tier 2 | AMER | Upgrade in progress | 421167 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | AM | Tier 2 | AMER | Upgrade in progress | 245751 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | DOPL | Tier 2 | JAPAC | Upgrade in progress | 206367 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | ASS | Tier 2 | EMEA | Upgrade in progress | 20000 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | TUI | Tier 2 | AMER | Upgrade in progress | 395528 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | CHI | Tier 2 | AMER | Upgrade in progress | 379749 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | AS | Tier 2 | EMEA | Upgrade in progress | 376770 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | I | Tier 2 | AMER | Upgrade in progress | 443561 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | PSPL | Tier 2 | JAPAC | Upgrade in progress | 364573 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | BISL | Tier 2 | EMEA | Upgrade in progress | 366444 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | WI | Tier 2 | AMER | Upgrade in progress | 101660 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | HFIC | Tier 2 | AMER | Upgrade in progress | 333600 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | MAGB | Tier 2 | JAPAC | Upgrade in progress | 330494 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | NH | Tier 2 | AMER | Upgrade in progress | 152626 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | BPC | Tier 2 | LATAM | Upgrade in progress | 318060 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | IS | Tier 2 | EMEA | Upgrade in progress | 315297 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | TCSL | Tier 2 | JAPAC | Upgrade in progress | 187210 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | UOEFA( | Tier 2 | EMEA | Upgrade in progress | 311744 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | CPPIB | Tier 2 | AMER | Upgrade in progress | 302500 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | CI | Tier 2 | AMER | Upgrade in progress | 270864 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | CMSACK | Tier 2 | EMEA | Upgrade in progress |  |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | O9CL | Tier 2 | JAPAC | Upgrade in progress | 169300 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | NL | Tier 2 | EMEA | Upgrade in progress | 247812 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | M | Tier 2 | EMEA | Upgrade in progress | 244200 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | ATC | Tier 2 | AMER | Upgrade in progress | 210260 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | HI | Tier 2 | AMER | Upgrade in progress | 144767 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | NGTL | Tier 2 | EMEA | Upgrade in progress | 234000 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | MSCC | Tier 2 | AMER | Upgrade in progress | 223497 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | UOTS( | Tier 2 | JAPAC | Upgrade in progress | 216801 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | NE( | Tier 2 | EMEA | Upgrade in progress | 200059 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | MOCAIT | Tier 2 | EMEA | Upgrade in progress | 214462 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | C( | Tier 2 | EMEA | Upgrade in progress | 18320 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | FTSL | Tier 2 | AMER | Upgrade in progress | 211680 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | C | Tier 2 | AMER | Upgrade in progress | 33192 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | TBL | Tier 2 | AMER | Upgrade in progress | 191798 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | TCC | Tier 2 | AMER | Upgrade in progress | 190832 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | TCH | Tier 2 | AMER | Upgrade in progress | 190663 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | PCC | Tier 2 | AMER | Upgrade in progress | 189000 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | MHIL | Tier 2 | JAPAC | Upgrade in progress | 185329 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | DTP | Tier 2 | JAPAC | Upgrade in progress | 178269 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | CAF | Tier 2 | AMER | Upgrade in progress | 177768 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | PSBI | Tier 2 | JAPAC | Upgrade in progress | 173307 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | PPSL | Tier 2 | JAPAC | Upgrade in progress | 166155 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | HA | Tier 2 | AMER | Upgrade in progress | 172218 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | DDSPL | Tier 2 | JAPAC | Upgrade in progress | 168600 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | T | Tier 2 | LATAM | Upgrade in progress | 157610 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | MI | Tier 2 | AMER | Upgrade in progress | 155635 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | TG | Tier 2 | JAPAC | Upgrade in progress | 31148 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | SL | Tier 2 | EMEA | Upgrade in progress | 149040 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | FBN | Tier 2 | AMER | Upgrade in progress | 141738 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | STL | Tier 2 | JAPAC | Upgrade in progress | 58744 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | TPFSGI | Tier 2 | AMER | Upgrade in progress | 137721 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | FMIC | Tier 2 | AMER | Upgrade in progress |  |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | ABL | Tier 2 | AMER | Upgrade in progress | 166795 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | FAI | Tier 2 | AMER | Upgrade in progress | 161409 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | 8L | Tier 2 | AMER | Upgrade in progress | 133750 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | WRSI | Tier 2 | AMER | Upgrade in progress | 148120 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | MI | Tier 2 | AMER | Upgrade in progress | 421200 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | INEI | Tier 2 | AMER | Upgrade in progress | 123584 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | LLHL | Tier 2 | AMER | Upgrade in progress | 122688 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | AI | Tier 2 | AMER | Upgrade in progress | 113106 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | SC | Tier 2 | AMER | Upgrade in progress | 112962 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | WBL | Tier 2 | JAPAC | Upgrade in progress | 112342 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | GBPL | Tier 2 | JAPAC | Upgrade in progress | 107982 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | C | Tier 2 | AMER | Upgrade in progress | 56330 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | BHOOL | Tier 2 | AMER | Upgrade in progress | 10152 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | GFL | Tier 2 | JAPAC | Upgrade in progress | 101250 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | LGL | Tier 2 | EMEA | Upgrade in progress | 266760 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | WCSHL | Tier 2 | AMER | Upgrade in progress | 76966 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | IP | Tier 2 | EMEA | Upgrade in progress | 3000 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | A | Tier 2 | EMEA | Upgrade in progress | 75900 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | C | Tier 2 | EMEA | Upgrade in progress | 68258 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | SL | Tier 2 | JAPAC | Upgrade in progress | 36000 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | PML | Tier 2 | JAPAC | Upgrade in progress | 29857 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | A(L | Tier 2 | EMEA | Upgrade in progress | 20500 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | AEHPL | Tier 2 | JAPAC | Upgrade in progress | 57598 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | F | Tier 2 | EMEA | Upgrade in progress | 25769 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | UTIPL | Tier 2 | JAPAC | Upgrade in progress | 50400 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | WGI | Tier 2 | AMER | Upgrade in progress | 45768 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | TB | Tier 2 | EMEA | Upgrade in progress | 45449 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | SGL | Tier 2 | AMER | Upgrade in progress | 44763 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | SHAAICL | Tier 2 | JAPAC | Upgrade in progress | 28800 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | BTUL | Tier 2 | AMER | Upgrade in progress | 144252 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | HIL | Tier 2 | JAPAC | Upgrade in progress | 21600 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | PGI | Tier 2 | JAPAC | Upgrade in progress | 17706 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | GFTPL | Tier 2 | JAPAC | Upgrade in progress | 14514 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | ESFBL | Tier 2 | JAPAC | Upgrade in progress | 12000 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending
0 | SEICL | Tier 2 | JAPAC | Upgrade in progress | 18612 |  |  | Awaiting Assessment |  | 0 | 0 | 0 | 0 | Assessment pending

## Blocker log
Account | Gap | Planned release | Default view | PM owner | Telemetry signal | Customer outcome | Description / how they use it (scale) | Workaround and who delivers it | Telemetry matched customer? | Release rank | Escalate? | Date validated | Notes
EC(TR | Asset audit trail | Jul 2027 | Major blocker | Guy Liberman | Flagged | HB | TKG clusters run about 40% of production workloads |  | Y | Sprint 4 |  | 2026-10-08
EC(TR | RQL to XQL custom rules | Oct 2026 to Jan 2027 | Major blocker | Ashwin Manekar | Flagged | WA | ~120 custom rules; 15 fail translation | PS rewrites the 15 failing rules before cutover | Y | Sprint 1 |  | 2026-10-08
EC(TR | GuardDuty ingestion | Jan 2027 | Validate in discovery | Elad Shuster | Flagged | NN | Findings duplicate Cortex Cloud detections |  | NFBNU | Sprint 2 |  | 2026-10-08

## Gap reference
Gap | Module | Description | Planned release | Default view | Telemetry field | Question to ask the customer | PM owner | Release rank | # accounts using | # accounts with hard blocker
Tanzu / PCF | CWP |  | Oct 2026 | Major blocker | Pending | DYPTTOPWAWSOYW | Daphna Shemesh | Sprint 1 | 0 | 0
Azure BYO Event Hub | CSPM |  | Oct 2026 | Major blocker | total_event_hub_accounts | DYOAWYOEH | Ashwin Manekar | Sprint 1 | 0 | 0
IBM Cloud rules (~71) | CSPM |  | Oct 2026 | Major blocker | IBM Usage - Telemetry | DYMICAROTPCCL | Ashwin Manekar | Sprint 1 | 0 | 0
Azure EAI | CSPM |  | Oct 2026 | Major blocker | requires_azure_eai_support | QTBDORPPJAMA | Ashwin Manekar | Sprint 1 | 0 | 0
Lightweight agent | Agent |  | Oct 2026 | Major blocker |  | DYRLKEODAWYATXAFUTLAIV | Daphna Shemesh | Sprint 1 | 0 | 0
IBM Cloud onboarding | Onboarding, CSPM, CWP |  | Oct 2026 | Major blocker |  | WOYAMICT | Chen Segelman | Sprint 1 | 0 | 0
Terraform onboarding (full lifecycle) | CSPM |  | Oct 2026 | Major blocker |  | DYMCAWT | Ashwin Manekar | Sprint 1 | 0 | 0
GCP Assured Workloads | Onboarding |  | Oct 2026 | Major blocker |  | DYRGAW(BVC | Avishai Moshka | Sprint 1 | 0 | 0
ServiceNow integration | AppSec |  | Oct 2026 | Major blocker |  | DYSATSAAWAOT | Andrew Scott | Sprint 1 | 0 | 0
Red Hat certified scanner | UVEM |  | Oct 2026 | Validate in discovery | Pending | DYSOORWADARRACS | Andrew Scott | Sprint 1 | 0 | 0
Alma Linux | CWP |  | Oct 2026 | Validate in discovery | Pending | DYRALHIOCAWS | Elad Shuster | Sprint 1 | 0 | 0
Jenkins image-scan plugin | CWP |  | Oct 2026 | Validate in discovery | Pending | DYSITTJP(A | Elad Shuster | Sprint 1 | 0 | 0
Compliance reporting | Compliance |  | Oct 2026 | Validate in discovery |  | QTBD | Ashwin Manekar | Sprint 1 | 0 | 0
xSPM inline scanner | CSPM |  | Oct 2026 | Validate in discovery |  | QTBD | Ashwin Manekar | Sprint 1 | 0 | 0
Terraform: agent, connector, registry | CSPM |  | Oct 2026 | Validate in discovery |  | CBTTPQ(2 | Ashwin Manekar | Sprint 1 | 0 | 0
RQL to XQL custom rules | CSPM |  | Oct 2026 to Jan 2027 | Major blocker | custom_config_policies | HMCRRDYHAHMFT | Ashwin Manekar | Sprint 1 | 1 | 0
CSP registry scan (non-onboarded accounts) | CWP |  | Jan 2027 | Major blocker | Pending | DYSRICATANO | Elad Shuster | Sprint 2 | 0 | 0
Network anomaly detection | CDR |  | Jan 2027 | Major blocker | Network Anomaly Alerts Count in CDR | DYUNAPAAOTA | Elad Shuster | Sprint 2 | 0 | 0
Granular module scoping | Onboarding, CWP, CSPM |  | Jan 2027 | Major blocker | has_granular_module_scoping | DYSFDAAITSO | Chen Segelman | Sprint 2 | 0 | 0
MSSP parent/child policies | CSPM |  | Jan 2027 | Major blocker | custom_policies_pushed_to_child | DYRPACTAPPTCT(TCJOA2 | Ashwin Manekar | Sprint 2 | 0 | 0
CLI remediation | CSPM |  | Jan 2027 | Major blocker | Rely on remediation rules | DYUCRMOA | Ashwin Manekar | Sprint 2 | 0 | 0
Asset audit trail | Platform |  | Jul 2027 | Major blocker | uses_asset_audit_trail | DYUACH | Guy Liberman | Sprint 4 | 1 | 1
Agentless: skip non-running VMs | CWP |  | Jan 2027 | Major blocker | Pending | HYTOSONM | Elad Shuster | Sprint 2 | 0 | 0
150K issue limit per module | Platform |  | Jan 2027 | Major blocker | Pending | WYE1IIAM | Sarit Tager | Sprint 2 | 0 | 0
Terraform provider gaps | CSPM |  | Jan 2027 | Major blocker | Pending | DYMPCTTTPAFW | Ashwin Manekar | Sprint 2 | 0 | 0
OCI template onboarding | CSPM |  | Jan 2027 | Major blocker | OCI_Usage_Telemetry | DYMOAHWTAO | Ashwin Manekar | Sprint 2 | 0 | 0
Alibaba template onboarding | CSPM |  | Jan 2027 | Major blocker | Alibaba_Usage_Telemetry | DYMAAHWTAO | Ashwin Manekar | Sprint 2 | 0 | 0
FedRAMP High | Cross modules |  | Jan 2027 | Major blocker | FedRamp High | ITTOFH | Eyal Keyton | Sprint 2 | 0 | 0
FedRAMP Moderate | Cross modules |  | Jan 2027 | Major blocker | FedRamp Moderate | ITTOFM | Eyal Keyton | Sprint 2 | 0 | 0
GuardDuty ingestion | CDR |  | Jan 2027 | Validate in discovery | Guard Duty Findings - 1mo | DYIGFADYNTBWCCD | Elad Shuster | Sprint 2 | 0 | 0
Flow logs in CDR | CDR |  | Jan 2027 | Validate in discovery | Flowlogs Usage in CDR | DYIFLAAUT | Elad Shuster | Sprint 2 | 0 | 0
Image analysis sandbox | CWP |  | Jan 2027 | Validate in discovery | Pending | DYRTIAS | Elad Shuster | Sprint 2 | 0 | 0
CIEM evidence | CSPM |  | Jan 2027 | Validate in discovery | manages_trusted_ips_via_api (mapping to confirm) | DYAUCOIA | Ashwin Manekar | Sprint 2 | 0 | 0
Trusted networks API | UVEM |  | Jan 2027 | Validate in discovery |  | DYMTIONTTA | Alexandre Cezar | Sprint 2 | 0 | 0
JFrog subdomains | CWP |  | Jan 2027 | Validate in discovery |  | DYSJARTUS | Elad Shuster | Sprint 2 | 0 | 0
AWS org Terraform onboarding | Onboarding |  | Jan 2027 | Validate in discovery |  | DYOAOWT | Eyal Rotberg | Sprint 2 | 0 | 0
Azure decrypt without ListKeys | CSPM |  | Jan 2027 | Validate in discovery |  | DYAPBTLP | Eyal Rotberg | Sprint 2 | 0 | 0
CSPM scan every 12h | CSPM |  | Jan 2027 | Validate in discovery |  | DYNPRMOTE2H | Ashwin Manekar | Sprint 2 | 0 | 0
XDR auto deploy | CWP |  | Jan 2027 | Validate in discovery | Pending | DYDDTA | Elad Shuster | Sprint 2 | 0 | 0
Multi-tenant (non-MSSP) | Platform, cross modules |  | Apr 2027 | Major blocker |  | DYRMTOTMC | Sarit Tager | Sprint 3 | 0 | 0
App Control | Agent |  | Jul 2027 | Major blocker |  | QTBD | Daphna Shemesh | Sprint 4 | 0 | 0
Cloud onboarding via API | Onboarding |  | TBC | Major blocker |  | DYOCAOTAOT | Eyal Rotberg | Sprint TBC | 0 | 0
AWS member account settings | Onboarding |  | TBC | Validate in discovery |  | DYNCIRNOTOTKTERAAEI | Eyal Rotberg | Sprint TBC | 0 | 0
Azure auth mode | Onboarding |  | TBC | Validate in discovery |  | DYPRASAAM(ISLADG | Eyal Rotberg | Sprint TBC | 0 | 0
Azure private resources | Onboarding |  | TBC | Validate in discovery |  | DYNVIAPR(KGPE | Eyal Rotberg | Sprint TBC | 0 | 0
IBM registry scanning | CWP |  | No date | Major blocker | Pending | DYSICCR | Avishai Moshka | Sprint TBC | 0 | 0
China regions | Onboarding, CSPM, CWP |  | No date | Major blocker | China coverage required | DYMAICRAOWC(MNC | Chen Segelman | Sprint TBC | 0 | 0
CortexCLI scan speed | CWP |  | No date | Major blocker |  | HMCSDYR | Ofer Hakimi | Sprint TBC | 0 | 0
Serverless runtimes | CWP |  | No date | Validate in discovery | Pending | DYRSORCCDNSAWS | Elad Shuster | Sprint TBC | 0 | 0
EKS Fargate | Agent |  | No date | Validate in discovery |  | DYPEOFAWSOYD | Daphna Shemesh | Sprint TBC | 0 | 0
AWS Inspector ingestion | UVEM |  | No date | Validate in discovery |  | DYIAIFAROT | Andrew Scott | Sprint TBC | 0 | 0
OCI outpost | Onboarding |  | No date | Validate in discovery |  | DYNSIYOOT | Avishai Moshka | Sprint TBC | 0 | 0
OIDC login | Platform |  | No date | Validate in discovery |  | DYIPRO | Ben Sack | Sprint TBC | 0 | 0
WAAS file upload rules | CWP |  | No date | Validate in discovery |  | DYUWFUR | Elad Shuster | Sprint TBC | 0 | 0
Terraform for XDR API | Agent |  | No date | Validate in discovery |  | QTBD | Daphna Shemesh | Sprint TBC | 0 | 0
Disable agentless when agent present | CWP |  | No date | Validate in discovery |  | CITCRI | Elad Shuster | Sprint TBC | 0 | 0
Dynamic URL | Platform |  | No date | Validate in discovery |  | DNRPCITCRI | Ben Sack | Sprint TBC | 0 | 0
Azure BYO app registration | Onboarding |  | Not planned | Validate in discovery |  | DNRPCIR(CIRE | Eyal Rotberg | Sprint TBC | 0 | 0
Other (not on gap list) |  |  | Unknown |  |  | DTBITLASTROPCI |  | Sprint TBC | 0 | 0

## Playbook feedback
Date | Account | TSE | Feedback type | What we learned | Suggested change (runbook, telemetry or product) | Owner | Status

## Lists
Planned release | Release rank | Unnamed: 2 | Rank | Readiness bucket | Unnamed: 5 | Tier | Upgrade status | Assessment status | Next step | Telemetry signal | Customer outcome | Telemetry matched customer? | Feedback type | Region
Oct 2026 | Sprint 1 |  | Sprint 1 | After October release |  | Tier 1 | In progress | Not started | Continue | Flagged | HB | Y | Telemetry correction | NAM
Oct 2026 to Jan 2027 | Sprint 1 |  | Sprint 2 | After January release |  | Tier 2 | Not started | Scheduled | Pause until release | Not flagged | WA | NFBNU | New blocker | LATAM
Jan 2027 | Sprint 2 |  | Sprint 3 | After April release or later |  |  |  | In progress | Escalate | No telemetry | NN | NUBNF | What worked | EMEA
Apr 2027 | Sprint 3 |  | 9 | No date |  |  |  | Complete |  |  | U | NT | What fell flat | JAPAC
Jul 2027 | Sprint 4
TBC | Sprint TBC
No date | Sprint TBC
Not planned | Sprint TBC
Unknown | Sprint TBC
Rank 2 for 'Oct 2026 to Jan 2027' plans on the later date. Ranks 9 count as no committed date.