## Key Instructions
Purpose of this template tracker
This is a standard template for the technical issues tracker to be maintained by each Top 100 account team. It should serve as a comprehensive record of all technical issues impacting the account, including parity gaps, bugs, feature requests, etc along with their status
Please note any issues that do not yet have a known / confirmed timeline should also be submitted to the Central COE tracker by the Account DC.

## Template
| From COE | From COE | From COE | From COE | From COE | From COE | DC to input | DC to input | DC to input | From COE | From COE | From COE | From COE | DC + Rep to input | DC + Rep to input
Account | COE Issue ID | Issue | Requirements | Expected outcomes | Priority | Issue Category | Upgrade blockers (as confirmed with customer) | JIRA or Asana link (if applicable) | TAC Case # (if applicable) | SPO DC assigned | Resource Name | Status - Has the question been answered definitively? | Timeline/ Answer | Comments from Account team (if gaps are still there for resolved items) | Notes, including workarounds provided (optional column)
John Hancock / Manulife | 749 | Agent resource requirements | Manulife is aware that the XDR agent will have a larger footprint than the prisma cloud defender. They would like a guidance on how to estimate the resource requirements for CPU/Memory to accurately estimate the cost | 1. Documented resource limits for min and max usage. They understand that this is environment dependent, but require a realistic estimate for their k8s clusters. 2. A call with the customer to discuss the capabilities of the new lightweight agent. | P1 - High | Parity Gap |  |  |  | Jack Valley | Yochai Kattan | Pending PM Acknowledgement | E.g., Known roadmap timeline (available in CC July release) | Manulife wants to test what is available today, which is the XDR agent. If the product is Beta ready, I can have a conversation with the customer to start testing with the beta version of the agent, assuming product team has high confidence on the stability of the agent. Main concern is the cost of operation due to increased resource usage. Other customers have also voiced their concern on the visibility of the container runtime, similar to Prisma Cloud Radar view.
John Hancock / Manulife | 748 | Custom/Manual Azure (Priority), AWS, GCP, and AliCloud onboarding with minimal permissions | Customer would like pre-create the app registration and roles. They require a supported and documented process for onboarding | Cortex Cloud documentation should provide detailed steps on how to manually onboard the service providers. Can we provide guidance on how to achieve this today in Cortex Cloud (2.0/2.1). This is becoming urgent. PS is helping to support the customer, but we need someone from the engineering team to walk them through the onboarding template an answer any questions they have on the onboarding steps in the terraform template. | P0 - Critical | Parity Gap | Yes |  |  | Jack Valley | Eyal Rotberg | Pending PM Acknowledgement |  | Working with Eyel Rotberg and Elad S. Some of the concerns are expected to be addressed in CC 2.1. Customer agreed to wait for CC 2.1 before onboarding. I am working on moving Manulife tenant upgrade to Batch 3. Customer has requested the following: 1. Documented steps to create the Service Principal in the Entera ID along with the permissions. If a naming convention needs to be followed, this should be specified as well. 2. A detailed description of the interactions between the different roles, cortex cloud and SP. 3. The permissions required for each of the roles and the explanation of each permission. Once the official 2.1 documentation is released, I will share it with the customer. The documentation for 2.0 was shared. Customer was not satisfied with it, as they don't understand how they are used (point 2 above). Eyal did share a preview of a detailed document with me for review. This document will unblock the customer. Unfortunately, this is internal and I can't share it with the customer. For this reason, next steps should be to arrange a call/workshop with Eyal's team and Manulife team to address their concerns.
John Hancock / Manulife | Added | Suppress IaC issue on the same page | In Checkov once you click into the URL in the console, you will be redirected to a page where you can directly suppress an IaC violation. Expecting the same on Cortex Cloud | feature parity with Prisma Cloud | P1 - High | Parity Gap |  |  | 4186880
John Hancock / Manulife | Added | Cortex Cli scan does not show passed and failed output | In Checkov in the pipeline output we are able to see both pass cases and fail cases. So we can make sure pass cases are scanned. | feature parity with Prisma Cloud | P1 - High | Parity Gap |  |  | 4186889
John Hancock / Manulife | Added | Cortex Cli does not expose flags that are in use in prisma cloud at Manulife. | --policy-metadata-filter policy.label=<label sf> --skip-check CKV* -o cli -o json EVAL_TF_PLAN_AFTER_UNKNOWN=true First flag is required to select the set of cortex appsec rules statically at build time for the ci scan Second flag is required to exclude appsec rules from the scan 3rd flag is something that the old bridgecrew team built for manulife to meet specific challenges to address terraform plan scanning | feature parity with Prisma Cloud First flag is required to select the set of cortex appsec rules statically at build time for the ci scan Second flag is required to exclude appsec rules from the scan 3rd flag is something that the old bridgecrew team built for manulife to meet specific challenges to address terraform plan scanning | P0 - Critical | Parity Gap | Yes |  | 4186899
John Hancock / Manulife | Added | Store and evaluate policy from local git repo (policy as code)/Cortex CLI not able to reference policy locally | In Checkov we can use the Checkov cli and referencing a local policies for testing. After that policy is tested we will promote it to our Cloud Platform. We need that feature for our automation | feature parity with Prisma Cloud In Prisma Cloud, customers can store the policy locally in a git repo and have it evaluated in the pipelines via local repo without having to pull them directly from Prisma Cloud. Manulife requires this capability to minimize changes to their build and test processes. Today, every (including custom) policies are tested and verified locally before being pushed to cortex. | P1 - High | Parity Gap |  |  | 4186920
John Hancock / Manulife | Added | Checkov/Cortex Cli unable to scan nested module | Ability to scan nested modules Checkov unable to scan nested module (causing false negative on the redis cache, not able to discover relationship between redis cache and diagnostics setting ) Previous ticket in Prisma: PANWRFE-I-1429 | Manulife has templatized their IaC code in modules. Treditional repository scanning methods will provide large number of false positives. For this reason, the ability to scan nested modules is essential for Manulife to adopt IaC scanning. | P1 - High | Feature Request |  | PANWRFE-I-1429 | 4186936
John Hancock / Manulife | Added | Package Risk for end of life and end of sale for both CWP and AppSec scanners | The vulnerability team at Manulife leverages Qualys to scan for vulnerabilities. This team is pushing to replace our CWP capabilities because our scanners can't produce EoL/EoS for packages. In Prisma Cloud we used PS team to deliver this capability. Customer expects this capability to be in product for cortex cloud. | The vulnerability team at Manulife leverages Qualys to scan for vulnerabilities. This team is pushing to replace our CWP capabilities because our scanners can't produce EoL/EoS for packages. In Prisma Cloud we used PS team to deliver this capability. Customer expects this capability to be in product for cortex cloud. | P1 - High | Feature Request | Yes | https://app.asana.com/1/11915891072957/project/1205799475462757/task/1212501212283336?focus=true | 4186938
John Hancock / Manulife | Added | No dedicated page for Cortex CLI scan for CWP. For appsec, scan results can be found at AppSec Module -> Scan -> CI Scan | No dedicated page for Cortex CLI scan for CWP. For appsec, scan results can be found at AppSec Module -> Scan -> CI Scan | A centralized place for all CWP cortex CLI scan | P1 - High | Parity Gap
John Hancock / Manulife | [5 empty] | Parity Gap
John Hancock / Manulife | [5 empty] | Parity Gap
John Hancock / Manulife
John Hancock / Manulife