## READMe
We need a list of all new CC upgrade projects that have recently kicked off or are pending kick off. All new upgrades are required to have a TSE sign off on the customers use cases and upgrade readiness.
Add the project Name in column A.

## Accounts
Name | PM |  | Renewal Date | What the Telemetry Says | What the Account Narrative says | Verdict - Ready to Upgrade
P-1894602, Fed- Marigold1 - CCU - BONO | Cristina Mateo |  | 2026-09-29 | No data | FedRAMP High (Q2) | Not Ready
P-1902101, Canada Pension Plan Investment Board - CCU - BONO | Marissa Zuliani |  | 2030-02-14 | Flow logs: anomaly detection in CDR (Q2) CLI resolution action (remediation) (Q2) Audit trails (asset timeline) (Q2/Q3) | EKS Fargate, Cloud Optimised Agent | Not Ready
P-1769145, Evergy, Inc CCU - PS | April Dumas | Customer kickoff | 2028-07-31 | EAI support for Azure (Q2) | No Hard Blockers | Not Ready (Unless the customer accepts the 12 delay on Azure Ingestion)
P-1906068, Nationwide Corporation - PS | Eric Black | Pending ETA on the validation process and sign off eta from TSE (Farooq Abrahem) | 2027-04-28 | No Hard Blockers | No Hard Blockers, but there are bugs | Check with Assigned TSE Farooq Abrahem
P-1889102, Sas Institute Inc. - CCU - BONO | Yonelly Gutierrez |  | 2028-06-02 | Flow logs: anomaly detection in CDR (Q2), EAI support for Azure (Q2) | Scheduled the kickoff call for 10/27 9:30 AM CDT. First meeting with the customer. | Check with Assigned TSE Khizar Karim
P-1883701, Sas Institute Inc. - CCU - AUTOMATION - BONO | Yonelly Gutierrez
P-1832403, Kaiser Permanente - CCU - BONO | Jakub Biziorek |  | 2027-05-21 | No Hard Blockers | The Kaiser team will review the scorecard to compare Cortex Cloud with the competitors. The account team plans to present an upgrade plan. Lots of functionailty to verify works for Kaiser in Q1 release | Check with the Assigned TSE Muhammad Ali
P-1873401, Fidelity National Financial, Inc. - CCU - BONO | Jakub Biziorek |  | 2029-07-30 | Audit trails (asset timeline) (Q2), EAI support for Azure (Q2) | Permissions Blockers (CSPM & CAS): FNF has raised two significant concerns: (1) overly permissive CSPM permissions in Cortex Cloud, and (2) highly permissive Azure DevOps Project Collection Administrator (PCA)-level permissions for CAS onboarding. Engineering and R&D teams are actively working to address both, with the CSPM Permissions Rationale & Feature Loss Matrix and provided intial set of responses/analysis of CSPM Listkeys and CAS PCA Azure DevOps permisisons to FNF. FNF will present to their CISO/CSO leadership team on MVP permisisons for CSPM, CAS, Code Scanning architecture on 10/26. Next session with FNF to review more on in-built security controls in Cortex Cloud to mitigate issues with stacking of permissions in Service Principle - is on 10/29. | Not ready (Until customer has no concerns on CSPM, CAS MVP permission deployment)
P-1847604, The PNC Financial Services Group, Inc. - CCU - BONO | Jakub Biziorek |  | 2027-05-30 | Audit trails (asset timeline) (Q2), EAI support for Azure (Q2) | Needs Updating | Check with Assigned TSE Farooq Abrahem
P-1852643, Mastercard Incorporated - PS | Jakub Biziorek |  | 2028-02-01 | Audit trails (asset timeline) (Q2), EAI support for Azure (Q2) | Multiple COE entries | Check with Assigned TSE Khizar Karim
P-1888301, Cenovus Energy Inc. | Cristina Mateo | Customer kickoff scheduled on 11/02/26 | 2027-12-15 | EAI support for Azure (Q2) | No Hard Blockers | TBC in Customer Kick Off Call
P-1889301, THE CLEARING HOUSE PAYMENTS COMPANY L.L.C. | Cristina Mateo | Customer kickoff scheduled on 10/29/26 | 2028-01-27 | Granular onboarding (scope per module) (Q2), Audit trails (asset timeline) (Q2/Q3) | No Hard Blockers | TBC in Customer Kick Off Call
P-1832402, John Hancock Financial | Ron Doria |  | 2027-11-30 | Lightweight Agent - Although out this 2.3 release the stronger security effectiveness capabilities looking for is not going to be available in the Cloud Optimised Agent until the next couple of main releases Audit Asset Trails - Are used regularly by this customer, 202 calls to these in the past 30 days and we are not expecting this feature until as late as June... Azure EAI (Q2) Alibaba Template Onboarding, (Q2) Network anomaly detection (Q2) CLI Remediation all due in the Q2 release China support - No date | Needs Updating | Check with Assigned TSE Vad Vadwlas
P-1864320, Universal Music Group | Ron Doria |  | 2028-07-31 | Flow logs: anomaly detection in CDR (Q2), EAI support for Azure (Q2) | Needs Updating | Not Ready (Unless the customer accepts the 12 delay on Azure Ingestion)
P-1873801, Rockwell Automation | Ron Doria |  | 2030-02-23 | No Data
P-1889302, Nutrien | Ron Doria |  | 2027-09-25 | Flow logs: anomaly detection in CDR (Q2) Granular onboarding (scope per module) (Q2) CLI resolution action (remediation) (Q2) Audit trails (asset timeline) (Q2/Q3) OCI: template-based onboarding (Q2) EAI support for Azure (Q2) | Needs Updating | Not Ready
P-1890101, Instinet Holdings Inc | Ron Doria |  | 2026-11-15 | No Hard Blockers | Instinet is a subsidiary of Nomura. Needs Updating | Renewal Date - Potential Compelling Event
P-1889783, Gilead Sciences | Ron Doria |  | 2031-04-29 | Flow logs: anomaly detection in CDR (Q2) Audit trails (asset timeline) (Q2/Q3) EAI support for Azure (Q2) | Needs Updating | Check with Assigned TSE - Akeim Findlay
P-1897319, Mayo Foundation For Medical Education And Research | April lasky