## How to use
Cortex Cloud upgrade: field assessment tracker
What this tracker answers for each account
1) Which technical blockers the customer has confirmed. 2) Which of those have no committed release date. 3) Which release clears the account, and the expected start date.
How to fill it in
1. Accounts tab: one row per account. Fill the white columns. Set Assessment status to Complete only when every relevant gap has been validated with the customer.
2. Blocker log tab: one row per gap discussed with the customer. Pick the account and gap from the dropdowns; release, default view and PM owner fill in automatically. This is for Roadmap blocking items only (Parity and Top 100 Account Feature Requests)
3. Set Customer outcome: Hard blocker, Workaround accepted, Not needed or Unknown. For a blocker that is not on the gap list, pick 'Other (not on gap list)' and describe it.
4. Record whether telemetry matched what the customer told you. These corrections improve telemetry for the next wave of accounts.
5. Playbook feedback tab: anything we should change in the runbook, telemetry or product.
How the readiness bucket is set (automatic)
Ready now: no validated hard blockers. Otherwise the latest planned release among the account's hard blockers sets the bucket.
No date: at least one hard blocker has No date, TBC, Not planned or Unknown. These rows show Escalate = Yes in the Blocker log; raise them with the PM owner.
'Oct 2026 to Jan 2027' (custom rule translation) counts as January, to plan on the later date. Apr and Jul 2027 both count as 'After April release or later'.
The bucket only shows once Assessment status is Complete. Set Expected start date yourself after agreeing it with the customer.
Legend
White cells: inputs. Grey cells: formulas, do not type over them. Grey italic rows: an example account to show the format; delete before use.
The full approach is in the TSE Field Assessment Guide.

## Summary
Field assessment summary
All figures update from the Accounts and Blocker log tabs. Grey cells are formulas; do not type over them.
Coverage
Accounts in scope | 198
Assessments complete | 0
% complete | 0%
Readiness buckets (completed assessments)
Bucket | # accounts | ARR ($M) | % of complete
Ready now | 0 | 0 | 0%
After October release | 0 | 0 | 0%
After January release | 0 | 0 | 0%
After April release or later | 0 | 0 | 0%
No date | 0 | 0 | 0%
Assessment pending | 197 | 87914454
Blockers
Validated hard blockers (all accounts) | 1
Hard blockers with no committed date | 0
Accounts with a no-date hard blocker | 0
Workarounds accepted | 1
Blockers not on the gap list | 0
Telemetry mismatches found | 1
Most common hard blockers: sort the Gap reference tab by its last column.

## Accounts
Account iD | Account | Tier | Region | Upgrade status | ARR ($M) | TSE | Companion (ride-along) | Assessment status | Assessment date | # gaps validated | # hard blockers | # hard blockers with no date | Latest release rank | Readiness bucket | Expected start date | Next step | Escalation reason | Notes
0017000000dN3dfAAC | Salesforce.Com, Inc. | Tier 1 | AMER | Upgrade in progress | 13604812 | Khizar Karim |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
00170000019KsKPAA0 | Zoom Video Communications, Inc. | Tier 1 | AMER | Upgrade in progress | 466800 | Z Yu |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000ZK0auAAD | Dell Inc. (Sell-to) | Tier 1 | AMER | Upgrade in progress | 3180264 | Tommy Song |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000ndlH6AAI | Ally Financial Inc. | Tier 1 | AMER | Upgrade in progress | 644000 | Steve Briand |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000qySjdAAE | Cognizant Technology Solutions Corporation | Tier 1 | AMER | Upgrade in progress | 3387281 | Alan Simpkins |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000PP73xAAD | Freddie Mac | Tier 1 | AMER | Upgrade in progress | 107136 | Ravi Badana |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0014u00002BGospAAD | Fed-Tulip38 | Tier 1 | AMER | Upgrade in progress | 2415715 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000jurAfAAI | MetLife, Inc. | Tier 1 | AMER | Upgrade in progress | 2191200 | Alex Reshetniak |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000bECMQAA4 | Broadcom Corporation | Tier 1 | AMER | Upgrade in progress | 2030431 | Z Yu |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000bE0yDAAS | Infosys Limited | Tier 1 | JAPAC | Upgrade in progress | 59568 | Syam Pillai |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000RGL6UAAX | American Express Company | Tier 1 | AMER | Upgrade in progress | 1872802 | Lindsey Smith |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0014u00001yJ3tHAAS | Volkswagen Software Asset Management GmbH | Tier 1 | EMEA | Upgrade in progress | 1794185 | Oleg Fiksel |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000rZ0dmAAC | Sabre GLBL Inc | Tier 1 | AMER | Upgrade in progress | 1751558 | Farooq Abrahem |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
00170000010kSQZAA2 | Inmobi | Tier 1 | JAPAC | Upgrade in progress | 1669027 | Syam Pillai |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000nyW67AAE | Zurich Financial Group AG | Tier 1 | AMER | Upgrade in progress | 1609632 | Tommy Song |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000qx7kfAAA | Fidelity National Financial, Inc. | Tier 1 | AMER | Upgrade in progress | 1483675 | Ravi Badana |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000ZN93ZAAT | Kaiser Permanente | Tier 1 | AMER | Upgrade in progress | 93655 | Muhammad Ali |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000cJCU8AAO | Cox Communications, Inc. | Tier 1 | AMER | Upgrade in progress | 55880 | Lauren Megrelis |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000bF5EOAA0 | The NASDAQ OMX Group, Inc. | Tier 1 | AMER | Upgrade in progress | 1247274 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000pdPvnAAE | Nationwide Building Society | Tier 1 | EMEA | Upgrade in progress | 441946 | Neel Dave |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000qx0YBAAY | Marriott International, Inc. | Tier 1 | AMER | Upgrade in progress | 1159779 | Khizar Karim |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000jFWBeAAO | Novo Nordisk A/S | Tier 1 | EMEA | Upgrade in progress | 1131332 | Amir Chamma |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0014u00001tEzw8AAC | Dh Business Services Llc | Tier 1 | AMER | Upgrade in progress | 773 | Khizar Karim |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0014u00001tDCt9AAG | Wipro Limited | Tier 1 | JAPAC | Upgrade in progress | 1081949 | Syam Pillai |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000PN6iDAAT | Tyson Foods, Inc. | Tier 1 | AMER | Upgrade in progress | 1069260 | Ravi Badana |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000y1HbLAAU | Hilton Worldwide Holdings Inc. | Tier 1 | AMER | Upgrade in progress | 203435 | Ravi Badana |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000bFPu8AAG | Equinix, Inc. | Tier 1 | AMER | Upgrade in progress | 955532 | Alex Reshetniak |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0014u00001yJU04AAG | Access Uk Ltd | Tier 1 | EMEA | Upgrade in progress | 678294 | Scott Orton |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000oqq3JAAQ | Engie | Tier 1 | EMEA | Upgrade in progress | 1602702 | Christopher Ley |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000jEETMAA4 | Medidata Solutions Worldwide | Tier 1 | AMER | Upgrade in progress | 807516 | Lauren Megrelis |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000gF8DtAAK | Abbott Laboratories | Tier 1 | AMER | Upgrade in progress | 807369 | Ravi Badana |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000001VuycpAAB | Airbus 1 | Tier 1 | EMEA | Upgrade in progress | 467026 | Daniel Tor |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000kbOIVAA2 | Lg Uplus Corp. | Tier 1 | JAPAC | Upgrade in progress | 755874 | Jane Shin |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0014u0000238d8uAAA | Corebridge Financial, Inc. | Tier 1 | AMER | Upgrade in progress | 36000 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0014u000029psomAAA | Optus Systems Pty Ltd | Tier 1 | JAPAC | Upgrade in progress | 325882 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000bFh2TAAS | The Chubb Corporation | Tier 1 | AMER | Upgrade in progress | 735868 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0010g00001aEcFbAAK | Aptiv Global Operations Limited | Tier 1 | EMEA | Upgrade in progress | 684959 | Simon Melotte |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000peemgAAA | Micron Technologies, Inc | Tier 2 | AMER | Upgrade in progress | 667543 | Lindsey Smith |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000qySuNAAU | Standard Bank Group Limited | Tier 1 | EMEA | Upgrade in progress | 651248 | Scott Orton |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000neSduAAE | Ulta Salon, Cosmetics & Fragrance, Inc | Tier 2 | AMER | Upgrade in progress | 638281 | Brian Lewis |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000f1hWDAAY | The Charles Schwab Corporation | Tier 2 | AMER | Upgrade in progress | 616279 | Vad Vadwlas |  | Pending |  | 15 | 0 | 0 | 0 | Assessment pending
00170000014LFmdAAG | Netsmart Technologies, Inc. | Tier 2 | AMER | Upgrade in progress | 591945 | Ravi Badana |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000kYwckAAC | L'Oreal | Tier 2 | EMEA | Upgrade in progress | 556043 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000os81PAAQ | Worley Parsons Limited | Tier 2 | AMER | Upgrade in progress | 448318 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000gGsAhAAK | Cantor Fitzgerald Technology Markets, LLC | Tier 2 | AMER | Upgrade in progress | 312371 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000q3Y2KAAU | Blue Cross Blue Shield Association (HQ) | Tier 2 | AMER | Upgrade in progress | 536097 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000cIg6KAAS | Vanderbilt Health | Tier 2 | AMER | Upgrade in progress | 414399 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000001XPl7OAAT | Tarjeta Naranja S.a. | Tier 2 | LATAM | Upgrade in progress | 521948 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000nyW1fAAE | Air Liquide S.A. | Tier 2 | EMEA | Upgrade in progress | 221649 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000tfianAAA | Diagnosticos da America S/A. | Tier 2 | LATAM | Upgrade in progress | 216512 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000tAmAHAA0 | Score Media and Gaming Inc. | Tier 2 | AMER | Upgrade in progress | 509056 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000lhzCGAAY | KeyBank National Association | Tier 1 | AMER | Upgrade in progress | 956789 | Tommy Song |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000qySf5AAE | Adani Enterprises Limited | Tier 2 | JAPAC | Upgrade in progress | [5 empty] | 0 | 0 | 0 | 0 | Assessment pending
0017000001V49vrAAB | Everbridge, Inc. | Tier 2 | AMER | Upgrade in progress | 63515 | Lauren Megrelis |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0014u00001mrMwXAAU | Nippon Life Insurance Australia and New Zealand Limited | Tier 2 | JAPAC | Upgrade in progress | 214458 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000drDq2AAE | Intrado Life & Safety | Tier 2 | AMER | Upgrade in progress | 376301 | Alex Reshetniak |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000YweyvAAB | Murata Manufacturing Co., Ltd. | Tier 2 | JAPAC | Upgrade in progress | 223538 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000nylXCAAY | Admiral Group Plc | Tier 2 | EMEA | Upgrade in progress | 432295 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000nyW8xAAE | MAPFRE S.A | Tier 2 | EMEA | Upgrade in progress | 432414 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000qySkiAAE | EDP Global | Tier 2 | EMEA | Upgrade in progress | 227991 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000001ITp6fAAD | Rakuten Usa, Inc. | Tier 2 | AMER | Upgrade in progress | 425742 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0014u000027qiy4AAA | Fed-Jasmine5 | Tier 2 | AMER | Upgrade in progress | 421167 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0010g00001hXpCsAAK | Applied Materials | Tier 2 | AMER | Upgrade in progress | 245751 | Muhammad Ali |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000nylpAAAQ | Whitbread | Tier 2 | EMEA | Upgrade in progress | 413281 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0014u00001x8IUDAA2 | Dyson Operations Pte. Ltd. | Tier 2 | JAPAC | Upgrade in progress | 206367 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000nesZZAAY | Amp Limited | Tier 2 | JAPAC | Upgrade in progress | 174291 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0014u00001tDTyIAAW | Ataccama Software, s.r.o. | Tier 2 | EMEA | Upgrade in progress | 20000 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000qyShCAAU | Bancolombia S.A. | Tier 2 | LATAM | Upgrade in progress | 338356 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000001AewZiAAJ | TriNet USA Inc. | Tier 2 | AMER | Upgrade in progress | 395528 | Z Yu |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0010g00001j5zIuAAI | STMicroelectronics | Tier 2 | EMEA | Upgrade in progress | 388943 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000001RMDCFAA5 | The Pokemon Company International Inc | Tier 2 | AMER | Upgrade in progress | 386259 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0014u00001uGbfaAAC | Kyndryl, Inc. | Tier 2 | AMER | Upgrade in progress | 382707 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000lAllhAAC | Cardinal Health, Inc. | Tier 2 | AMER | Upgrade in progress | 379749 | Brian Lewis |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000YfwM2AAJ | A&O Shearman | Tier 2 | EMEA | Upgrade in progress | 376770 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000cIUW0AAO | Intact | Tier 2 | AMER | Upgrade in progress | 443561 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000001NWi6iAAD | PEXA Services Pty Ltd | Tier 2 | JAPAC | Upgrade in progress | 364573 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000cIF9wAAG | Baring Investment Services Limited | Tier 2 | EMEA | Upgrade in progress | 366444 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000gE2ySAAS | Wawa, Inc. | Tier 2 | AMER | Upgrade in progress | 101660 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000orFxrAAE | Rockwell Automation, Incorporated | Tier 2 | AMER | Upgrade in progress | 353220 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000mAYzCAAW | Sanofi S.A | Tier 2 | EMEA | Upgrade in progress | 352512 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000WRcO6AAL | HARTFORD FIRE INSURANCE COMPANY | Tier 2 | AMER | Upgrade in progress | 333600 | Alan Simpkins |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0014u000026KaSRAA0 | Malaysia Aviation Group Berhad | Tier 2 | JAPAC | Upgrade in progress | 330494 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000001GFR0OAAX | Banco Pichincha C.A. | Tier 2 | LATAM | Upgrade in progress | 318060 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000yNYy4AAG | Yardi Systems, Inc. | Tier 2 | AMER | Upgrade in progress | 315725 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000ylwVDAAY | IVECO SPA | Tier 2 | EMEA | Upgrade in progress | 315297 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
001700000137YtQAAU | Tata Consultancy Services Limited | Tier 2 | JAPAC | Upgrade in progress | 187210 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000zfLmuAAE | Union of European Football Associations (UEFA) | Tier 2 | EMEA | Upgrade in progress | 311744 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000001XPurFAAT | Stone Pagamentos S.a. | Tier 2 | LATAM | Upgrade in progress | 443998 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
00170000011uEWiAAM | CRISIL LIMITED | Tier 2 | JAPAC | Upgrade in progress | 97271 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0010g00001j5KivAAE | Canada Pension Plan Investment Board | Tier 2 | AMER | Upgrade in progress | 302500 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000001RLJkdAAH | California Employment Development Department | Tier 2 | AMER | Upgrade in progress | 292000 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0010g00001lRVosAAG | Porto Seguro Seguro Saude S/A | Tier 1 | LATAM | Upgrade in progress | 785724 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000qySs8AAE | PPG Industries, Inc. | Tier 2 | AMER | Upgrade in progress | 34948 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000jtfNDAAY | CHS Inc. | Tier 2 | AMER | Upgrade in progress | 270864 | Ravi Badana |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
00170000010Dsg3AAC | CompuGroup Medical SE and Co KGaA | Tier 2 | EMEA | Upgrade in progress | [5 empty] | 0 | 0 | 0 | 0 | Assessment pending
0017000001MCHlVAAX | One 97 Communications Limited | Tier 2 | JAPAC | Upgrade in progress | 169300 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000001V6ZhvAAF | Nuvei Ltd | Tier 2 | EMEA | Upgrade in progress | 247812 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000nyWK2AAM | Mercadona | Tier 2 | EMEA | Upgrade in progress | 244200 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000UUsrOAAT | Advocate Aurora Health | Tier 2 | AMER | Upgrade in progress | 240106 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000wKwTRAA0 | Allegiant Travel Company | Tier 2 | AMER | Upgrade in progress | 210260 | Alex Reshetniak |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000cKVeuAAG | HealthPartners, Inc. | Tier 2 | AMER | Upgrade in progress | 144767 | Brian Lewis |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0014u000027pKgOAAU | National Gas Transmission Limited | Tier 2 | EMEA | Upgrade in progress | 234000 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000mmAPGAA2 | Richemont International SA | Tier 2 | EMEA | Upgrade in progress | 234000 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000jucKCAAY | NYU Langone Health | Tier 2 | AMER | Upgrade in progress | 66959 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000bGHkaAAG | Primerica Financial Services, LLC | Tier 2 | AMER | Upgrade in progress | 227460 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000t9fPSAAY | Memorial Sloan-Kettering Cancer Center | Tier 2 | AMER | Upgrade in progress | 223497 | Lauren Megrelis |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000mlohXAAQ | Publix Super Markets, Inc. | Tier 2 | AMER | Upgrade in progress | 223480 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000cLVIzAAO | Fifth Third Bancorp | Tier 2 | AMER | Upgrade in progress | 145800 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000n7h74AAA | Foundation Medicine, Inc. | Tier 2 | AMER | Upgrade in progress | 220104 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000jFpGaAAK | IBERDROLA, S.A. | Tier 2 | EMEA | Upgrade in progress | 15541 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000kYov4AAC | University of Technology, Sydney (UTS) | Tier 2 | JAPAC | Upgrade in progress | 216801 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000jsdwkAAA | Omnicell | Tier 2 | AMER | Upgrade in progress | 215911 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0014u000026M7eFAAS | NEOM Energy (ENOWA) | Tier 2 | EMEA | Upgrade in progress | 200059 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0014u000022YArZAAW | Ministry of Communications and Information Technology | Tier 2 | EMEA | Upgrade in progress | 214462 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000lkNkTAAU | Carrefour (Spain) | Tier 2 | EMEA | Upgrade in progress | 18320 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000001K1QrCAAV | Franklin Templeton Services, LLC | Tier 2 | AMER | Upgrade in progress | 211680 | Z Yu |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000jFlOWAA0 | Ameriprise Financial, Inc. | Tier 2 | AMER | Upgrade in progress | 207000 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000LKb1aAAD | Connection | Tier 2 | AMER | Upgrade in progress | 33192 | Alan Simpkins |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0014u000028xwJGAAY | Alpiq Ag | Tier 2 | EMEA | Upgrade in progress | 198244 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000001DcUXgAAN | BAJAJ FINANCE LIMITED | Tier 2 | JAPAC | Upgrade in progress | 195069 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000peq8uAAA | Tory Burch LLC | Tier 2 | AMER | Upgrade in progress | 191798 | Khizar Karim |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000dK3YiAAK | The Coca-Cola Company | Tier 2 | AMER | Upgrade in progress | 190832 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000mir1qAAA | Texas Children's Hospital | Tier 2 | AMER | Upgrade in progress | 190663 | Farooq Abrahem |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000hb81BAAQ | Suez | Tier 2 | EMEA | Upgrade in progress | 180374 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000001NUIVSAA5 | Personal Capital Corporation | Tier 2 | AMER | Upgrade in progress | 189000 | Alex Reshetniak |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000mA9HIAA0 | Mitsubishi Heavy Industries, Ltd. | Tier 2 | JAPAC | Upgrade in progress | 185329 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000dwYJnAAM | Dialog Telekom Plc | Tier 2 | JAPAC | Upgrade in progress | 178269 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000nyStKAAU | Crum and Forster | Tier 2 | AMER | Upgrade in progress | 177768 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0014u0000238m8wAAA | PT Super Bank Indonesia | Tier 2 | JAPAC | Upgrade in progress | 173307 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0014u000027r2h7AAA | Paytm Payments Services Limited | Tier 2 | JAPAC | Upgrade in progress | 166155 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000ymVodAAE | HCL Americas | Tier 2 | AMER | Upgrade in progress | 172218 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0010g00001mqdS9AAI | Darwinbox Digital Solutions Private Limited | Tier 2 | JAPAC | Upgrade in progress | 168600 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000001XPu6EAAT | National Skill Development Corporation (NSDC) | Tier 2 | JAPAC | Upgrade in progress | 158825 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000nbVORAA2 | Transbank | Tier 2 | LATAM | Upgrade in progress | 157610 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0010g00001dm3HmAAI | Emis Group Plc | Tier 2 | EMEA | Upgrade in progress | 157379 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0014u00001x8rNFAAY | Movable Ink | Tier 2 | AMER | Upgrade in progress | 155635 | Lauren Megrelis |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000t9bIaAAI | TRANSURBAN GROUP | Tier 2 | JAPAC | Upgrade in progress | 31148 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000orq3TAAQ | Novant Health | Tier 2 | AMER | Upgrade in progress | 152626 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000ju7cDAAQ | DXC Technology Company | Tier 2 | AMER | Upgrade in progress | 151973 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000ymt9iAAA | Snam Rete Gas S.p.A. | Tier 2 | EMEA | Upgrade in progress | 75816 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0010g00001ZYGl0AAH | Silverfort Ltd | Tier 2 | EMEA | Upgrade in progress | 149040 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000001JMtxAAAT | New York City Fire Department (FDNY) | Tier 2 | AMER | Upgrade in progress | 144274 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000vj0ESAAY | Flagstar Bank, N.A. | Tier 2 | AMER | Upgrade in progress | 141738 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000dIyCpAAK | Singapore Telecommunications Limited | Tier 2 | JAPAC | Upgrade in progress | 58744 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000001KpWicAAF | Playtika | Tier 2 | EMEA | Upgrade in progress | [5 empty] | 0 | 0 | 0 | 0 | Assessment pending
0017000000dx6OMAAY | The PNC Financial Services Group, Inc. | Tier 2 | AMER | Upgrade in progress | 137721 | Farooq Abrahem |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000nBDuXAAW | Factory Mutual Insurance Co | Tier 2 | AMER | Upgrade in progress |  | Khizar Karim |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000Le8WUAAZ | Alliance Berstein L.P. | Tier 2 | AMER | Upgrade in progress | 166795 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0010g00001j75vWAAQ | ezCater | Tier 2 | AMER | Upgrade in progress | 138242 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000MfHihAAF | Franciscan Alliance, Inc. | Tier 2 | AMER | Upgrade in progress | 161409 | Farooq Abrahem |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000001QXMvoAAH | 84.51 Llc | Tier 2 | AMER | Upgrade in progress | 133750 | Ravi Badana |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
001700000137WgRAAU | Wind River Systems, Inc. | Tier 2 | AMER | Upgrade in progress | 148120 | Farooq Abrahem |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000scHxAAAU | Meijer, Inc. | Tier 2 | AMER | Upgrade in progress | 421200 | Muhammad Ali |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000p63kNAAQ | Enterprise Products Partners L.P. | Tier 2 | AMER | Upgrade in progress | 85680 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000001Kr9P1AAJ | Onity Group Inc. | Tier 2 | AMER | Upgrade in progress | 126158 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000Wc7W0AAJ | ISO New England Inc. | Tier 2 | AMER | Upgrade in progress | 123584 | Alan Simpkins |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000001Da8uNAAR | LINEAGE LOGISTICS HOLDINGS, LLC | Tier 2 | AMER | Upgrade in progress | 122688 | Z Yu |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0014u000027r4ZjAAI | Xaira Therapeutics | Tier 2 | AMER | Upgrade in progress | 117656 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000ZLRJNAA5 | Aaron's, Inc. | Tier 2 | AMER | Upgrade in progress | 113106 | Muhammad Ali |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000rXvEBAA0 | Skillsoft Corporation | Tier 2 | AMER | Upgrade in progress | 112962 | Alan Simpkins |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000nBPYcAAO | Wesfarmers Bunnings Limited | Tier 2 | JAPAC | Upgrade in progress | 112342 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0014u00001v8iIBAAY | GXS BANK PTE. LTD | Tier 2 | JAPAC | Upgrade in progress | 107982 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000woxnfAAA | CSC | Tier 2 | AMER | Upgrade in progress | 56330 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000hckcpAAA | Baker Hughes Oilfield Operations LLC | Tier 2 | AMER | Upgrade in progress | 10152 | Tommy Song |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000zhcptAAA | Gold Fields Limited | Tier 2 | JAPAC | Upgrade in progress | 101250 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000jElv6AAC | Excellus BlueCross BlueShield | Tier 2 | AMER | Upgrade in progress | 98496 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0010g00001lQxmeAAC | LIBERTY GROUP LTD | Tier 2 | EMEA | Upgrade in progress | 266760 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000ZKsJcAAL | Los Angeles Unified School District | Tier 2 | AMER | Upgrade in progress | 148176 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000WdcfKAAR | ADT Security Services, Inc. | Tier 1 | AMER | Upgrade in progress | 1003668 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0010g00001j76JOAAY | White Cap Supply Holdings, LLC | Tier 2 | AMER | Upgrade in progress | 76966 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000yNK04AAG | Israel Police | Tier 2 | EMEA | Upgrade in progress | 3000 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000s7lJ5AAI | Aumovio | Tier 2 | EMEA | Upgrade in progress | 75900 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0010g00001doVZcAAM | Evergy, Inc | Tier 2 | AMER | Upgrade in progress | 74000 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000nyW8cAAE | CODERE | Tier 2 | EMEA | Upgrade in progress | 68258 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000001NU1MzAAL | STARHUB LTD. | Tier 2 | JAPAC | Upgrade in progress | 36000 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0014u00001yK2WxAAK | Paytm Money Limited | Tier 2 | JAPAC | Upgrade in progress | 29857 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000ka7MQAAY | Tnuva | Tier 2 | EMEA | Upgrade in progress | 20400 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000dJHLUAA4 | Amdocs (Israel) Ltd. | Tier 2 | EMEA | Upgrade in progress | 20500 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
00170000012OqvJAAS | ALINTA ENERGY HOLDINGS PTY LTD | Tier 2 | JAPAC | Upgrade in progress | 57598 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000001RLMsFAAX | FQE | Tier 2 | EMEA | Upgrade in progress | 25769 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0014u0000236TrDAAU | Us Technology International Private Limited | Tier 2 | JAPAC | Upgrade in progress | 50400 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000lhJ3CAAU | Willdan Group, Inc. | Tier 2 | AMER | Upgrade in progress | 45768 | Z Yu |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0010g00001ZZTxNAAX | Tandem Bank | Tier 2 | EMEA | Upgrade in progress | 45449 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0014u000021JsYaAAK | Scientific Games LLC | Tier 2 | AMER | Upgrade in progress | 44763 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000001A81xLAAR | City of Virginia Beach | Tier 2 | AMER | Upgrade in progress | 43524 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000001VuZoWAAV | Rategain IT Solutions Pvt Ltd | Tier 2 | JAPAC | Upgrade in progress | 43267 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000001CLpBBAA1 | Banco Industrial SA | Tier 2 | LATAM | Upgrade in progress | 16069 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0010g00001inQVCAA2 | Star Health And Allied Insurance Company Limited | Tier 2 | JAPAC | Upgrade in progress | 28800 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000WT6RiAAL | BCD Travel USA LLC | Tier 2 | AMER | Upgrade in progress | 144252 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
00170000018SSaSAAW | TEXAS ROADHOUSE, INC. | Tier 2 | AMER | Upgrade in progress | 22032 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
00170000016V5wnAAC | HAVELLS INDIA LIMITED | Tier 2 | JAPAC | Upgrade in progress | 21600 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000vEvgOAAS | Aditya Birla Management Corporation Ltd. | Tier 2 | JAPAC | Upgrade in progress | 18263 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0010g00001lS14uAAC | Galactus Funware Technology Private Limited | Tier 2 | JAPAC | Upgrade in progress | 14514 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0010g00001j3CUfAAM | Equitas Small Finance Bank Limited | Tier 2 | JAPAC | Upgrade in progress | 12000 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000vj9YgAAI | National Hockey League | Tier 2 | AMER | Upgrade in progress | 261040 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000dMIaMAAW | Loblaws Inc. | Tier 1 | AMER | Upgrade in progress | 1008784 | Steve Briand |  | Pending |  | 0 | 0 | 0 | 0 | Assessment pending
0017000000vFYOcAAO | Shinko Electric Industries Co., Ltd. | Tier 2 | JAPAC | Upgrade in progress | 18612 |  |  |  |  | 0 | 0 | 0 | 0 | Assessment pending

## Sheet1
TSE
Khizar Karim
Z Yu
Tommy Song
Steve Briand
Alan Simpkins
Ravi Badana
Alex Reshetniak
Syam Pillai
Lindsey Smith
Oleg Fiksel
Farooq Abrahem
Muhammad Ali
Lauren Megrelis
Neel Dave
Amir Chamma
Scott Orton
Christopher Ley
Daniel Tor
Jane Shin
Simon Melotte
Brian Lewis
Vad Vadwlas

## Blocker log
Account | Gap | Planned release | Default view | PM owner | Telemetry signal | Customer outcome | Description / how they use it (scale) | Workaround and who delivers it | Telemetry matched customer? | Sprint | Release rank | Escalate? | Date validated | Notes
Example Corp (ignore this row) | Audit Asset Trail | #N/A | #N/A | #N/A | Flagged | Hard blocker | TKG clusters run about 40% of production workloads |  | Yes |  | #N/A | #N/A | 2026-10-08
Example Corp (ignore this row) | RQL to XQL custom rules | Oct 2026 to Jan 2027 | Major blocker | Ashwin Manekar | Flagged | Workaround accepted | ~120 custom rules; 15 fail translation | PS rewrites the 15 failing rules before cutover | Yes |  | 2 |  | 2026-10-08
Example Corp (ignore this row) | GuardDuty ingestion | Jan 2027 | Validate in discovery | Elad Shuster | Flagged | Not needed | Findings duplicate Cortex Cloud detections |  | No, flagged but not used |  | 2 |  | 2026-10-08
Salesforce.Com, Inc. | Tanzu / PCF | Oct 2026 | Major blocker | Daphna Shemesh | [6 empty] | 1
The Charles Schwab Corporation | RQL to XQL custom rules | Oct 2026 to Jan 2027 | Major blocker | Ashwin Manekar | Flagged | WA | 365 custom policies in translation scope; 260 translated as of 9/29. Translation paused 10/13 while PS built asset group automation. | PS (Phelipe) translating policies by hand; 105 remaining. | Y | Sprint 1 | No | 2026-09-29 | Telemetry custom_config_policies = 601 against 365 in scope; confirm what the other 236 are.
The Charles Schwab Corporation | Terraform provider gaps | Jan 2027 | Major blocker | Ashwin Manekar | No telemetry | HB | Schwab manages rules and controls through Terraform (policy as code). Provider support for rules tracked as COE 524. |  | NT | Sprint 2 | No | 2026-10-19 | Case 04248274 / XSUP-78801: Terraform control creation works in test, fails in production. PM: Bhushan.
The Charles Schwab Corporation | Asset audit trail | Jul 2027 | Major blocker | Guy Liberman | Flagged | U | Telemetry: uses_asset_audit_trail = 1, 15 asset audit trail API calls in 30 days. What calls it and whether Schwab depends on it is not yet confirmed. |  |  | Sprint 4 | No |  | Telemetry unblock date Jan 2027; Gap reference says Jul 2027. Both after Schwab's end-of-November target.
The Charles Schwab Corporation | Terraform onboarding (full lifecycle) | Oct 2026 | Major blocker | Ashwin Manekar | No telemetry | U | Schwab pushed back on the standard Terraform onboarding template and wants to customize it. Azure, onboarded later in Q4, creates the service principal with Terraform from the onboarding wizard app ID. | Service principal via Terraform azuread_service_principal (Phelipe guidance to Justin). | NT | Sprint 1 | No |  | Template pushback from Upgrade Notes (Combined Database, last edited Jul 1 2026). Confirm status with Schwab.
The Charles Schwab Corporation | Other (not on gap list) | Unknown |  |  | No telemetry | HB | Issue to Jira automation: Schwab named automatic issue creation in Jira as an open cutover blocker. |  | NT | Sprint TBC | Yes | 2026-10-16 | No product owner identified. Confirm date of the Schwab statement.
The Charles Schwab Corporation | Other (not on gap list) | Unknown |  |  | No telemetry | HB | Compliance categories and subcategories via API: Schwab builds custom compliance standards through the API. Subcategory required in production, optional in test. |  | NT | Sprint TBC | Yes | 2026-09-02 | Case 04194314 (closed 9/24). Case says full support 11/22; PMs said Oct 19 it is available. PM: Swapnil.
The Charles Schwab Corporation | Other (not on gap list) | Unknown |  |  | No telemetry | WA | Asset groups from account tags: Schwab organizes ownership by cloud account tags; no native tag inheritance into asset groups or business applications. | PS automation (Phelipe) creates asset groups and business applications from account tags. AWS sent 10/16, GCP in progress, Azure next. | NT | Sprint TBC | No | 2026-10-20
The Charles Schwab Corporation | Other (not on gap list) | Unknown |  |  | No telemetry | WA | GCP firewall IP and CIDR lookup: Find every GCP firewall rule whose source range contains a given IP. 192 classic VPC rules (49 distinct ranges) plus firewall policies. | XQL lookup validated in Schwab's tenant for policies and VPC rules (TSE). No automatic flagging yet. | NT | Sprint TBC | No | 2026-10-16 | XPANDR-15405. Search: Guy Li (UAI). Config rule CIDR functions: Bhushan.
The Charles Schwab Corporation | Other (not on gap list) | Unknown |  |  | No telemetry | U | GCP address group resolution in firewall policy: Resolve project and organization scoped address groups to IP ranges. Not yet known whether Schwab's policies reference address groups. |  | NT | Sprint TBC | No |  | XPANDR-15404, 15401. Planned end of September, delivery not confirmed. PM: Maur.
The Charles Schwab Corporation | Other (not on gap list) | Unknown |  |  | No telemetry | U | AWS audit log ingestion: Schwab asked for EventBridge S3 event format and S3 to SQS without SNS. CSE guidance: neither supported, SNS required. | SNS intermediary; acceptability to Schwab not confirmed. | NT | Sprint TBC | No |  | Specialist review requested Oct 5. PM: Guy Liberman.
The Charles Schwab Corporation | Other (not on gap list) | Unknown |  |  | No telemetry | U | Default policy parity with Prisma Cloud: Justin asked for parity with Prisma Cloud default policies (Sep 10). |  | NT | Sprint TBC | No |  | No owner.
The Charles Schwab Corporation | Other (not on gap list) | Unknown |  |  | No telemetry | U | Rules API for automation: Schwab automation reads rules through the unified rules API; linked out-of-the-box rules were excluded. | Retest after fix. | NT | Sprint TBC | No |  | Case 04220471, fix scheduled Oct 18 hotfix. PM: Amir (AppSec).
The Charles Schwab Corporation | Other (not on gap list) | Unknown |  |  | No telemetry | U | GCP Parameter Manager ingestion: Feature request: parameters describe, list, versions. Driver: IAM controls and audit logging for compliance and change management. |  | NT | Sprint TBC | No |  | Expected Nov 22, depends on release batch. PM: Maur.
The Charles Schwab Corporation | Other (not on gap list) | Unknown |  |  | No telemetry | U | AWS Lambda image attribute ingestion: Feature request for Lambda image attributes such as ImageUri. |  | NT | Sprint TBC | No |  | Expected Nov 22, depends on release batch. PM: Maur.
The Charles Schwab Corporation | Other (not on gap list) | Unknown |  |  | No telemetry | U | KSPM rules for read-only roles: Read-only users cannot see KSPM rules through Access Management roles. |  | NT | Sprint TBC | No |  | Case 04247910, TAC researching. KSPM PM not identified.

## Gap reference
Gap | Module | Planned release | Default view | Telemetry field | Question to ask the customer | PM owner | Release rank | # accounts using | # accounts with hard blocker
Tanzu / PCF | CWP | Oct 2026 | Major blocker | Pending | Do you protect Tanzu, TKG or PCF workloads, and what share of your workloads? | Daphna Shemesh | 1 | 0 | 0
Azure BYO Event Hub | CSPM | Oct 2026 | Major blocker | total_event_hub_accounts | Did you onboard Azure with your own Event Hub? | Ashwin Manekar | 1 | 0 | 0
IBM Cloud rules (~71) | CSPM | Oct 2026 | Major blocker | IBM Usage - Telemetry | Do you monitor IBM Cloud and rely on the policies Cortex Cloud lacks? | Ashwin Manekar | 1 | 0 | 0
Azure EAI | CSPM | Oct 2026 | Major blocker | requires_azure_eai_support | Question to be defined. October reaches Prisma parity; January adds more APIs. | Ashwin Manekar | 1 | 0 | 0
Lightweight agent | Agent | Oct 2026 | Major blocker | None | Do you run large Kubernetes estates on Defender, and will you accept the XDR agent footprint until the lightweight agent is validated? | Daphna Shemesh | 1 | 0 | 0
IBM Cloud onboarding | Onboarding, CSPM, CWP | Oct 2026 | Major blocker | None | Which of your accounts monitor IBM Cloud today? | Chen Segelman | 1 | 0 | 0
Terraform onboarding (full lifecycle) | CSPM | Oct 2026 | Major blocker | None | Do you manage cloud accounts with Terraform? | Ashwin Manekar | 1 | 1 | 0
GCP Assured Workloads | Onboarding | Oct 2026 | Major blocker | None | Do you run GCP Assured Workloads? (ETA being validated, CRTX-231176) | Avishai Moshka | 1 | 0 | 0
ServiceNow integration | AppSec | Oct 2026 | Major blocker | None | Do you send alerts to ServiceNow, and are workflows automated on them? | Andrew Scott | 1 | 0 | 0
Red Hat certified scanner | UVEM | Oct 2026 | Validate in discovery | Pending | Do you scan OpenShift or RHEL/UBI workloads, and does a regulation require a certified scanner? | Andrew Scott | 1 | 0 | 0
Alma Linux | CWP | Oct 2026 | Validate in discovery | Pending | Do you run Alma Linux hosts, images or containers, and what share? | Elad Shuster | 1 | 0 | 0
Jenkins image-scan plugin | CWP | Oct 2026 | Validate in discovery | Pending | Do you scan images through the Jenkins plugin? (workaround available) | Elad Shuster | 1 | 0 | 0
Compliance reporting | Compliance | Oct 2026 | Validate in discovery | None | Question to be defined. | Ashwin Manekar | 1 | 0 | 0
xSPM inline scanner | CSPM | Oct 2026 | Validate in discovery | None | Question to be defined. | Ashwin Manekar | 1 | 0 | 0
Terraform: agent, connector, registry | CSPM | Oct 2026 | Validate in discovery | None | Covered by the Terraform provider question (Jan 2027). | Ashwin Manekar | 1 | 0 | 0
RQL to XQL custom rules | CSPM | Oct 2026 to Jan 2027 | Major blocker | custom_config_policies | How many custom RQL rules do you have, and how many fail translation? | Ashwin Manekar | 2 | 2 | 0
CSP registry scan (non-onboarded accounts) | CWP | Jan 2027 | Major blocker | Pending | Do you scan registries in cloud accounts that are not onboarded? | Elad Shuster | 2 | 0 | 0
Network anomaly detection | CDR | Jan 2027 | Major blocker | Network Anomaly Alerts Count in CDR | Do you use network anomaly policies and act on their alerts? | Elad Shuster | 2 | 0 | 0
Granular module scoping | Onboarding, CWP, CSPM | Jan 2027 | Major blocker | has_granular_module_scoping | Do you scope features differently across accounts in the same org? | Chen Segelman | 2 | 0 | 0
MSSP parent/child policies | CSPM | Jan 2027 | Major blocker | custom_policies_pushed_to_child | Do you run parent and child tenants, and push policies to child tenants? (ETA to confirm: Jan or Apr 2027) | Ashwin Manekar | 2 | 0 | 0
CLI remediation | CSPM | Jan 2027 | Major blocker | Rely on remediation rules | Do you use CLI remediation, manual or automatic? | Ashwin Manekar | 2 | 0 | 0
Asset audit trail | Platform | Jan 2027 | Major blocker | uses_asset_audit_trail | Do you use asset configuration history? | Guy Liberman | 2 | 1 | 0
Agentless: skip non-running VMs | CWP | Jan 2027 | Major blocker | Pending | Have you turned off scanning of non-running machines? | Elad Shuster | 2 | 0 | 0
150K issue limit per module | Platform | Jan 2027 | Major blocker | Pending | Would you exceed 150K issues in any module? | Sarit Tager | 2 | 0 | 0
Terraform provider gaps | CSPM | Jan 2027 | Major blocker | Pending | Do you manage Prisma Cloud through the Terraform provider, and for what? | Ashwin Manekar | 2 | 1 | 0
OCI template onboarding | CSPM | Jan 2027 | Major blocker | OCI_Usage_Telemetry | Do you monitor OCI, and how were those accounts onboarded? | Ashwin Manekar | 2 | 0 | 0
Alibaba template onboarding | CSPM | Jan 2027 | Major blocker | Alibaba_Usage_Telemetry | Do you monitor Alibaba, and how were those accounts onboarded? | Ashwin Manekar | 2 | 0 | 0
FedRAMP High | Cross modules | Jan 2027 | Major blocker | FedRamp High | Is the tenant on FedRAMP High? | Eyal Keyton | 2 | 0 | 0
FedRAMP Moderate | Cross modules | Jan 2027 | Major blocker | FedRamp Moderate | Is the tenant on FedRAMP Moderate? | Eyal Keyton | 2 | 0 | 0
GuardDuty ingestion | CDR | Jan 2027 | Validate in discovery | Guard Duty Findings - 1mo | Do you ingest GuardDuty findings, and do you need them beyond what Cortex Cloud detects? | Elad Shuster | 2 | 0 | 0
Flow logs in CDR | CDR | Jan 2027 | Validate in discovery | Flowlogs Usage in CDR | Do you ingest flow logs and actively use them? | Elad Shuster | 2 | 0 | 0
Image analysis sandbox | CWP | Jan 2027 | Validate in discovery | Pending | Do you run the image analysis sandbox? | Elad Shuster | 2 | 0 | 0
CIEM evidence | CSPM | Jan 2027 | Validate in discovery | manages_trusted_ips_via_api (mapping to confirm) | Do you actively use CIEM or IAM analysis? | Ashwin Manekar | 2 | 0 | 0
Trusted networks API | UVEM | Jan 2027 | Validate in discovery | None | Do you manage trusted IPs or networks through the API? | Alexandre Cezar | 2 | 0 | 0
JFrog subdomains | CWP | Jan 2027 | Validate in discovery | None | Do you scan JFrog Artifactory registries that use subdomains? | Elad Shuster | 2 | 0 | 0
AWS org Terraform onboarding | Onboarding | Jan 2027 | Validate in discovery | None | Do you onboard AWS organizations with Terraform? | Eyal Rotberg | 2 | 0 | 0
Azure decrypt without ListKeys | CSPM | Jan 2027 | Validate in discovery | None | Does your Azure policy block the ListKeys permission? | Eyal Rotberg | 2 | 0 | 0
CSPM scan every 12h | CSPM | Jan 2027 | Validate in discovery | None | Do you need posture results more often than every 24 hours? | Ashwin Manekar | 2 | 0 | 0
XDR auto deploy | CWP | Jan 2027 | Validate in discovery | Pending | Do you deploy Defenders through auto-defend? | Elad Shuster | 2 | 0 | 0
Multi-tenant (non-MSSP) | Platform, cross modules | Apr 2027 | Major blocker | None | Do you run more than one tenant, managed centrally? | Sarit Tager | 3 | 0 | 0
App Control | Agent | Jul 2027 | Major blocker | None | Question to be defined. | Daphna Shemesh | 3 | 0 | 0
Cloud onboarding via API | Onboarding | TBC | Major blocker | None | Do you onboard cloud accounts only through API or Terraform? | Eyal Rotberg | 9 | 0 | 0
AWS member account settings | Onboarding | TBC | Validate in discovery | None | Do you need custom IAM role names or templates, or to keep the existing role ARN and External ID? | Eyal Rotberg | 9 | 0 | 0
Azure auth mode | Onboarding | TBC | Validate in discovery | None | Does your policy require a specific Azure auth method? (WIF is supported; likely a documentation gap) | Eyal Rotberg | 9 | 0 | 0
Azure private resources | Onboarding | TBC | Validate in discovery | None | Do you need visibility into Azure private resources? (no known gap per engineering) | Eyal Rotberg | 9 | 0 | 0
IBM registry scanning | CWP | No date | Major blocker | Pending | Do you scan IBM Cloud Container Registry? | Avishai Moshka | 9 | 0 | 0
China regions | Onboarding, CSPM, CWP | No date | Major blocker | China coverage required | Do you monitor accounts in China regions, and on which clouds? (escalate; make no commitments) | Chen Segelman | 9 | 0 | 0
CortexCLI scan speed | CWP | No date | Major blocker | None | How many CI scans do you run? | Ofer Hakimi | 9 | 0 | 0
Serverless runtimes | CWP | No date | Validate in discovery | Pending | Do you run serverless on runtimes Cortex Cloud does not support, and what share? | Elad Shuster | 9 | 0 | 0
EKS Fargate | Agent | No date | Validate in discovery | None | Do you protect EKS on Fargate, and what share of your deployment? | Daphna Shemesh | 9 | 0 | 0
AWS Inspector ingestion | UVEM | No date | Validate in discovery | None | Do you ingest AWS Inspector findings and rely on them? | Andrew Scott | 9 | 0 | 0
OCI outpost | Onboarding | No date | Validate in discovery | None | Do you need scanning inside your own OCI tenancy? | Avishai Moshka | 9 | 0 | 0
OIDC login | Platform | No date | Validate in discovery | None | Does your identity policy require OIDC? | Ben Sack | 9 | 0 | 0
WAAS file upload rules | CWP | No date | Validate in discovery | None | Do you use WAAS file upload rules? | Elad Shuster | 9 | 0 | 0
Terraform for XDR API | Agent | No date | Validate in discovery | None | Question to be defined. | Daphna Shemesh | 9 | 0 | 0
Disable agentless when agent present | CWP | No date | Validate in discovery | None | Capture if the customer raises it. | Elad Shuster | 9 | 0 | 0
Dynamic URL | Platform | No date | Validate in discovery | None | Do not raise proactively; capture if the customer raises it. | Ben Sack | 9 | 0 | 0
Azure BYO app registration | Onboarding | Not planned | Validate in discovery | None | Do not raise proactively; capture if raised (more common in regulated environments). | Eyal Rotberg | 9 | 0 | 0
Other (not on gap list) |  | Unknown |  |  | Describe the blocker in the log and set the release once product confirms it. |  | 9 | 11 | 0

## Playbook feedback
Date | Account | TSE | Feedback type | What we learned | Suggested change (runbook, telemetry or product) | Owner | Status

## Lists
Planned release | Release rank | Rank | Readiness bucket | Tier | Upgrade status | Assessment status | Next step | Telemetry signal | Customer outcome | Telemetry matched customer? | Feedback type | Region
Oct 2026 | 1 | 1 | After October release | Tier 1 | In progress | Not started | Continue | Flagged | Hard blocker | Yes | Telemetry correction | NAM
Oct 2026 to Jan 2027 | 2 | 2 | After January release | Tier 2 | Not started | Scheduled | Pause until release | Not flagged | Workaround accepted | No, flagged but not used | New blocker | LATAM
Jan 2027 | 2 | 3 | After April release or later |  |  | In progress | Escalate | No telemetry | Not needed | No, used but not flagged | What worked | EMEA
Apr 2027 | 3 | 9 | No date |  |  | Complete |  |  | Unknown | No telemetry | What fell flat | JAPAC
Jul 2027 | 3
TBC | 9
No date | 9
Not planned | 9
Unknown | 9
Rank 2 for 'Oct 2026 to Jan 2027' plans on the later date. Ranks 9 count as no committed date.