## Read Me
How this tracker works
What to edit
White cells | Inputs. Owners update these.
Grey cells | Formulas. Do not edit.
Last updated (Accounts) | Owners update this date every time they touch the row. Rows older than 7 days are flagged.
Rules the Dashboard enforces
Gate breach (RED) | Stage is Onboarding or later and Go / No Go is not Go.
Gate breach (RED) | Any pre-onboarding step marked Skipped.
Gate breach (RED) | A committed onboarding date is entered before Go / No Go is Go. No date is committed until the gate is green.
Gate breach (RED) | Stage is Done but 'All scanners returning data' is empty. Done means every enabled scanner returns data, not Terraform applied.
Watch item (AMBER) | No onboarding record linked; no named engineer during Pre or Onboarding; retro not held within 48 hours of the scanner date; next action missing or overdue; row not updated in 7 days; a Done step with no evidence link where evidence is required.
How to add an account
Add a row in Accounts. In Checklist, copy the 16 rows of any account to the bottom, change the account name and reset Status to Not started. Fill Named owner for each step; Row flag fills from its formula.
How the runbook stays in sync
The Steps tab mirrors the runbook . Change it only when a retro changes the runbook. Checklist rows carry the step text; when the runbook changes a step, update Steps and the matching Checklist rows.

## Steps and Roles
Step ID | Phase | Step | Owner role | Exit criterion | Evidence required (Y/N) | Evidence / asset expected | Deviations logged | Rank key (helper)
P1 | Pre | Copy the Onboarding Record template and link it in the Accounts tab | TSE | Record link populated in Accounts tab | Y | Onboarding Record link | 0 | 0.098
P2 | Pre | Technical assessment of the environment | TSE | Section A environment profile complete | Y | Onboarding Record, Section A | 0 | 0.097
P3 | Pre | Permission pre-flight run on named admins | TSE | Pre-flight output attached; every failure resolved or logged as a deviation | Y | Pre-flight script output | 0 | 0.096
P4 | Pre | Engineering review of regions, services, APIs and SCPs; known noise suppressed in the back end before Terraform | Named engineer | Suppression applied before Terraform runs (pre-facto, not post-onboarding cleanup) | Y | Engineering review notes / suppression confirmation | 0 | 0.095
P5 | Pre | Branch decisions recorded (Outpost vs Cloud Scan, StackSet vs per-account Terraform, Azure vs AWS, Fed tenant, least-privilege Azure) | TSE | Section B branch decisions complete | Y | Onboarding Record, Section B | 0 | 0.094
P6 | Pre | Workshop with TSE, TPE and PS on the wizard and the decision branches | TSE | Workshop held; date recorded | N |  | 0 | 0.093
P7 | Pre | Customer briefed on findings vs. issues and on not editing templates | TSE | Briefing held with the customer's named admins | N |  | 0 | 0.092
P8 | Pre | Go / No Go with a committed date | TSE + PS | P1 to P7 Done or N/A; Go recorded in Accounts tab; date committed. If any gate item is not met, the date moves | Y | Onboarding Record, Section C | 0 | 0.091
D1 | During | First account or subscription onboarded and validated end to end before the org | PS | One account or subscription ingesting with every enabled scanner returning data | Y | Validation evidence | 0 | 0.09
D2 | During | Tiger team plus named engineer on the call reading errors live | Named engineer | Named engineer attended the event call | N |  | 0 | 0.089
D3 | During | Every deviation logged against the step where it occurred | PS | Every deviation in the Deviations tab with a step ID | N |  | 0 | 0.088
D4 | During | Org onboarding run; Terraform applied | PS | Terraform apply date recorded in Accounts tab (this is not the exit) | N |  | 0 | 0.087
V1 | Post | Validation checklist run against the definition of done | TSE + PS | All accounts ingesting and every enabled scanner returning data; date recorded in Accounts tab | Y | Onboarding Record, Section E | 0 | 0.086
V2 | Post | Enablement session on findings vs. issues | TSE | Session held | N |  | 0 | 0.085
V3 | Post | Retro within 48 hours of V1 | TSE | Retro held; outputs logged to runbook change log (Vitaliy), docs feedback log and pre-flight script | Y | Onboarding Record, Section F | 0 | 0.084
V4 | Post | Handover to CS | TSE | Section G complete; CS owner named | Y | Onboarding Record, Section G | 0 | 0.083

## Dashboard
8 |  | 0 |  | – |  | 8 |  | 0
Events run (of 13) |  | Clean exits |  | Median days |  | Accounts with a gate breach |  | Deviations logged
Stage is Onboarding or later |  | Done with no open blocker |  |  |  | See Health = RED |  | All accounts
Pipeline by stage
Not started | Pre-onboarding | Onboarding | Post-onboarding | Done | On hold
4 | 1 | 6 | 1 | 1 | 0
Account spotlight: gate compliance and next action
Account | Stage | PS | TSE | Pre steps complete | Go / No Go | Days, Terraform to all scanners | Deviations | Gate breaches | Watch items | Gate Check | Flags | Next action | Owner | Due
Zoom Video | Onboarding | Matthew Dombrowski | Z Yu | 0 / 8 | Not held |  | 0 | 2 | 3 | RED | Onboarding started without a Go Date committed before the gate is green No onboarding record linked No named engineer Not updated in 7+ days | Once issues are resolved, we can continue onboarding GCP and Azure (if customer wants to in migration) | Matt-PS Mark - EE Zoom - Cloud Ops | TBD
Broadcom | Onboarding | Stephen Lovett | Z Yu | 3 / 8 | Not held |  | 0 | 1 | 3 | RED | Onboarding started without a Go No named engineer Not updated in 7+ days Done step missing evidence | Pending customer's internal ticket to have cloud admin review outpost terraform files and apply.
Telecom Guatemala | Done | Ariel Nin | Fabio Cezar (DC) | 4 / 8 | Not held | #VALUE! | 0 | 2 | 2 | RED | Onboarding started without a Go Date committed before the gate is green Retro overdue (48h rule) Not updated in 7+ days | Continue the Cortex Cloud CSPM deployment | Ariel Nin - Professional Services | 10/05 onwards
FIS Global | Not started | Stephen Lovett | Harold Moore (DC) | 0 / 8 | Not held |  | 0 | 0 | 1 | AMBER | Not updated in 7+ days | Customer has onboarded all their Cloud Providers however seeing errors and warnings. Customer has indicated expanding security capabilities and pivot towards outposts.
Fidelity | Pre-onboarding | Stephen Lovett | Ravi Badana | 0 / 8 | Not held |  | 0 | 0 | 2 | AMBER | No named engineer Not updated in 7+ days | Customer is conducting POV
DOI | Not started | Stephen Lovett |  | 0 / 8 | Not held |  | 0 | 0 | 1 | AMBER | Not updated in 7+ days | On hold
Marriott | Onboarding | Bliss Jourdan | Khizar Karim | 0 / 8 | Not held |  | 0 | 2 | 3 | RED | Onboarding started without a Go Date committed before the gate is green No named engineer Not updated in 7+ days No next action set
Honeywell International | Onboarding | Kirk Preston |  | 0 / 0 | Not held | #VALUE! | 0 | 2 | #VALUE! | RED | #VALUE! | Download CSP templates for internal review proactively. | TBD | TBD
Salesforce - ESS org | Not started | Bliss Jourdan | Khizar Karim | 0 / 8 | Not held |  | 0 | 0 | 2 | AMBER | Not updated in 7+ days No next action set
Mastercard | Not started |  | Khizar Karim | 0 / 0 | Not held |  | 0 | 0 | 2 | AMBER | Not updated in 7+ days No next action set
Thales | Onboarding | Ariel Nin | Steve Briand | 0 / 8 | Not held |  | 0 | 2 | 4 | RED | Onboarding started without a Go Date committed before the gate is green No onboarding record linked No named engineer Not updated in 7+ days No next action set
Verizon | Post-onboarding |  | Farooq Abrahem | 0 / 0 | Not held |  | 0 | 1 | 3 | RED | Onboarding started without a Go No onboarding record linked Not updated in 7+ days No next action set
Early Warning Services LLC | Onboarding |  | Lindsey Smith | 0 / 8 | Not held |  | 0 | 1 | 4 | RED | Onboarding started without a Go No onboarding record linked No named engineer Not updated in 7+ days No next action set

## Accounts
# | Account | Motion | Prior onboarding issues | Cloud(s) | PS consultant | TSE | Named engineer | Onboarding Record link | Stage | Go / No Go | Go / No Go date | Committed onboarding date | Terraform apply date | All scanners returning data successfully (date) | Retro date | CS handover date | Open blocker | Next action | Next action owner | Next action due | Last updated | Notes
1 | Zoom Video | Upgrade | N | AWS, OCI, GCP, Azure | Matthew Dombrowski | Z Yu |  |  | Onboarding |  |  | TBD |  |  |  |  | Issues with asset count in Cortex. Currently being looked at by engineering. | Once issues are resolved, we can continue onboarding GCP and Azure (if customer wants to in migration) | Matt-PS Mark - EE Zoom - Cloud Ops | TBD | 2026-09-23
2 | Broadcom | Upgrade | N | Azure, GCP, AWS | Stephen Lovett | Z Yu |  | OAE - Broadcom - Tracker | Onboarding | Not held | [7 empty] | Pending customer's internal ticket to have cloud admin review outpost terraform files and apply. |  |  | 2026-09-23
3 | Telecom Guatemala | Net new | Y | Azure | Ariel Nin | Fabio Cezar (DC) |  | OAE - Telecomunicaciones De Guatemala - Tracker | Done |  |  | 2026-09-24 | 09/24 Reapplied on 09/30 | 2026-10-05 |  | N/A | N/A | Continue the Cortex Cloud CSPM deployment | Ariel Nin - Professional Services | 10/05 onwards | 2026-10-08 | N/A
4 | FIS Global | Net new | Y | Azure, GCP, AWS, OCI | Stephen Lovett | Harold Moore (DC) |  | OAE - FIS Global - Tracker | Not started | [8 empty] | Customer has onboarded all their Cloud Providers however seeing errors and warnings. Customer has indicated expanding security capabilities and pivot towards outposts. |  |  | 2026-09-23
5 | Fidelity | Upgrade | Y | Azure | Stephen Lovett | Ravi Badana |  | OAE - FnF - Tracker | Pre-onboarding | [8 empty] | Customer is conducting POV |  |  | 2026-09-23
6 | DOI | Upgrade | Y | Azure, GCP, AWS | Stephen Lovett |  |  | OAE - DOI - Tracker | Not started | [8 empty] | On hold |  |  | 2026-09-23
7 | Marriott | Upgrade | N | AWS, Azure, Alibaba, GCP, OCI | Bliss Jourdan | Khizar Karim |  | OAE - Marriott - Tracker | Onboarding |  |  | Next Sprint. Within 2 weeks. |  |  |  |  | Want updates to the AWS CFT. Want to remove the lamdba function and connect manually. |  |  |  | 2026-10-08
8 | Honeywell International | Upgrade | N | AWS, Azure, Alibaba, GCP, OCI | Kirk Preston |  |  | Honeywell Onboarding + Tracker | Onboarding |  |  | ETA, Likely 10/27 or 11/3 (contd) | AWS Commercial: 9/17/26, GCP Commercial: 2026-10-15 | AWS Commerical: 2026-09-24 |  | N/A | Customer is evaluating compliance reporting parity before onboarding more accounts/CSPs. This could delay onboarding. | Download CSP templates for internal review proactively. | TBD | TBD | 2026-10-19
9 | Salesforce - ESS org | Upgrade | N |  | Bliss Jourdan | Khizar Karim |  |  | Not started | [11 empty] | 2026-09-23
10 | Mastercard | Upgrade | Unknown |  |  | Khizar Karim |  |  | Not started | [11 empty] | 2026-09-23
11 | Thales | Upgrade | Y | AWS,GCP | Ariel Nin | Steve Briand |  |  | Onboarding | Not held |  | 2026-09-29 |  |  |  |  | Csutomer is evaluating Cortex Cloud vs Wiz and has experienced various Errors and Warnings during onboarding.
12 | Verizon | Upgrade | Y | AWS |  | Farooq Abrahem |  |  | Post-onboarding |  |  |  | 2026-09-28 |  |  |  | We have onboarded Verizon to AWS outpost. They are evaluating Wiz too. |  |  |  |  | Over the past week, we have been working through a series of AWS governance blockers with Verizon to deploy the Cortex Cloud Outpost, starting with a Duplicate tag key 'Name' error that was resolved by removing the 'Name' tag from the Terraform variables. After that, scans failed with InvalidSnapshot.NotFound because Verizon's internal auto-tagging Lambda (VzGov-Tagger) was aggressively deleting our temporary snapshots for lacking mandatory corporate tags, which the customer has since mitigated by updating their Lambda configuration to whitelist the Cortex role. Today, however, we are seeing new failures—specifically Workload status not found and InvalidVolume.NotFound (likely due to Cortex targeting ephemeral volumes that their auto-scaler already terminated). Because the customer is experiencing severe migration fatigue and Wiz is actively courting them, we cannot ask Verizon to pull more CloudTrail logs. We urgently need backend engineering to review our internal telemetry for the Outpost proxy connection and fleet logs to determine why the scanner workloads are failing to launch or report back.
13 | Early Warning Services LLC | Upgrade | Y | AWS, Azure |  | Lindsey Smith |  |  | Onboarding | [7 empty] | EWS are experiencing very low resource accounts indicating issues with onboarding |  |  |  |  | AWS is their largest cloud provider and primary focus. EWS have tried to onboard on their own, with multiple tries, but not full success.
14
15
16
17
18
19
20

## Checklist
Account | Step ID (P = Pre, D = During, V = Post) | Step (full text and exit criterion in Steps tab) | Owner role | Named owner | Status | Date done | Evidence / asset link | Evidence required | Notes | Row flag
Zoom Video | P1 | Onboarding Record created and linked | TSE | Z Yu | Not started |  |  | Y
Zoom Video | P2 | Technical assessment | TSE | Z Yu | Not started |  |  | Y
Zoom Video | P3 | Permission pre-flight on named admins | TSE | Z Yu | Not started |  |  | Y
Zoom Video | P4 | Engineering review; pre-facto noise suppression | Named engineer |  | Not started |  |  | Y |  | Owner missing
Zoom Video | P5 | Branch decisions recorded | TSE | Z Yu | Not started |  |  | Y
Zoom Video | P6 | Wizard and branches workshop (TSE, TPE, PS) | TSE | Z Yu | Not started |  |  | N
Zoom Video | P7 | Customer briefing: findings vs. issues, no template edits | PS | Matthew Dombrowski | Not started |  |  | N
Zoom Video | P8 | Go / No Go with committed date | TSE + PS | Z Yu / Matthew Dombrowski | Not started |  |  | Y
Zoom Video | D1 | First account validated end to end | PS | Matthew Dombrowski | Not started |  |  | Y
Zoom Video | D2 | Named engineer on the call | Named engineer |  | Not started |  |  | N |  | Owner missing
Zoom Video | D3 | Deviations logged live | PS | Matthew Dombrowski | Not started |  |  | N
Zoom Video | D4 | Org onboarded; Terraform applied | PS | Matthew Dombrowski | Not started |  |  | N
Zoom Video | V1 | Validation: all scanners returning data | TSE + PS | Z Yu / Matthew Dombrowski | Not started |  |  | Y
Zoom Video | V2 | Enablement session | TSE | Z Yu | Not started |  |  | N
Zoom Video | V3 | Retro within 48 hours | TSE | Z Yu | Not started |  |  | Y
Zoom Video | V4 | CS handover | TSE | Z Yu | Not started |  |  | Y
Broadcom | P1 | Onboarding Record created and linked | TSE | Z Yu | Not started |  |  | Y
Broadcom | P2 | Technical assessment | TSE | Z Yu | Done | 2026-09-08 |  | Y |  | Evidence missing
Broadcom | P3 | Permission pre-flight on named admins | TSE | Z Yu | Not started |  |  | Y
Broadcom | P4 | Engineering review; pre-facto noise suppression | Named engineer | OAE - Broadcom - Tracker | Not started |  |  | Y
Broadcom | P5 | Branch decisions recorded | TSE | Z Yu | Not started |  |  | Y
Broadcom | P6 | Wizard and branches workshop (TSE, TPE, PS) | TSE | Z Yu | Done | 2026-09-10 |  | N
Broadcom | P7 | Customer briefing: findings vs. issues, no template edits | PS | Stephen Lovett | Done | 2026-09-15 |  | N
Broadcom | P8 | Go / No Go with committed date | TSE + PS | Z Yu / Stephen Lovett | Not started |  |  | Y
Broadcom | D1 | First account validated end to end | PS | Stephen Lovett | Not started |  |  | Y
Broadcom | D2 | Named engineer on the call | Named engineer | OAE - Broadcom - Tracker | Not started |  |  | N
Broadcom | D3 | Deviations logged live | PS | Stephen Lovett | Not started |  |  | N
Broadcom | D4 | Org onboarded; Terraform applied | PS | Stephen Lovett | Not started |  |  | N
Broadcom | V1 | Validation: all scanners returning data | TSE + PS | Z Yu / Stephen Lovett | Not started |  |  | Y
Broadcom | V2 | Enablement session | TSE | Z Yu | Not started |  |  | N
Broadcom | V3 | Retro within 48 hours | TSE | Z Yu | Not started |  |  | Y
Broadcom | V4 | CS handover | TSE | Z Yu | Not started |  |  | Y
Telecom Guatemala | P1 | Onboarding Record created and linked | TSE | Fabio Cezar (DC) | Done |  | OAE - Telecomunicaciones De Guatemala - Tracker | Y |  | Date missing
Telecom Guatemala | P2 | Technical assessment | TSE | Fabio Cezar (DC) | Done |  | OAE - Telecomunicaciones De Guatemala - Tracker | Y |  | Date missing
Telecom Guatemala | P3 | Permission pre-flight on named admins | TSE | Fabio Cezar (DC) | Done |  | OAE - Telecomunicaciones De Guatemala - Tracker | Y |  | Date missing
Telecom Guatemala | P4 | Engineering review; pre-facto noise suppression | Named engineer | OAE - Telecomunicaciones De Guatemala - Tracker | Not started |  |  | Y
Telecom Guatemala | P5 | Branch decisions recorded | TSE | Fabio Cezar (DC) | Not started |  |  | Y
Telecom Guatemala | P6 | Wizard and branches workshop (TSE, TPE, PS) | TSE | Fabio Cezar (DC) | Not started |  |  | N
Telecom Guatemala | P7 | Customer briefing: findings vs. issues, no template edits | PS | Ariel Nin | Not started |  |  | N
Telecom Guatemala | P8 | Go / No Go with committed date | TSE + PS | Fabio Cezar (DC) / Ariel Nin | Done | 2026-09-24 | OAE - Telecomunicaciones De Guatemala - Tracker | Y
Telecom Guatemala | D1 | First account validated end to end | PS | Ariel Nin | Done | 2026-09-30 | OAE - Telecomunicaciones De Guatemala - Tracker | Y
Telecom Guatemala | D2 | Named engineer on the call | Named engineer | OAE - Telecomunicaciones De Guatemala - Tracker | Not started |  |  | N
Telecom Guatemala | D3 | Deviations logged live | PS | Ariel Nin | Done | 2026-09-24 | OAE - Telecomunicaciones De Guatemala - Tracker | N
Telecom Guatemala | D4 | Org onboarded; Terraform applied | PS | Ariel Nin | Done | 2026-09-30 | OAE - Telecomunicaciones De Guatemala - Tracker | N | Azure Dev completed
Telecom Guatemala | V1 | Validation: all scanners returning data | TSE + PS | Fabio Cezar (DC) / Ariel Nin | Done | 2026-10-05 | OAE - Telecomunicaciones De Guatemala - Tracker | Y
Telecom Guatemala | V2 | Enablement session | TSE | Fabio Cezar (DC) | Done | 2026-10-05 |  | N
Telecom Guatemala | V3 | Retro within 48 hours | TSE | Fabio Cezar (DC) | Done | 2026-10-07 | OAE - Telecomunicaciones De Guatemala - Tracker | Y
Telecom Guatemala | V4 | CS handover | TSE | Fabio Cezar (DC) | Not started |  |  | Y
FIS Global | P1 | Onboarding Record created and linked | TSE | Harold Moore (DC) | Not started |  |  | Y
FIS Global | P2 | Technical assessment | TSE | Harold Moore (DC) | Not started |  |  | Y
FIS Global | P3 | Permission pre-flight on named admins | TSE | Harold Moore (DC) | Not started |  |  | Y
FIS Global | P4 | Engineering review; pre-facto noise suppression | Named engineer | OAE - FIS Global - Tracker | Not started |  |  | Y
FIS Global | P5 | Branch decisions recorded | TSE | Harold Moore (DC) | Not started |  |  | Y
FIS Global | P6 | Wizard and branches workshop (TSE, TPE, PS) | TSE | Harold Moore (DC) | Not started |  |  | N
FIS Global | P7 | Customer briefing: findings vs. issues, no template edits | PS | Stephen Lovett | Not started |  |  | N
FIS Global | P8 | Go / No Go with committed date | TSE + PS | Harold Moore (DC) / Stephen Lovett | Not started |  |  | Y
FIS Global | D1 | First account validated end to end | PS | Stephen Lovett | Not started |  |  | Y
FIS Global | D2 | Named engineer on the call | Named engineer | OAE - FIS Global - Tracker | Not started |  |  | N
FIS Global | D3 | Deviations logged live | PS | Stephen Lovett | Not started |  |  | N
FIS Global | D4 | Org onboarded; Terraform applied | PS | Stephen Lovett | Not started |  |  | N
FIS Global | V1 | Validation: all scanners returning data | TSE + PS | Harold Moore (DC) / Stephen Lovett | Not started |  |  | Y
FIS Global | V2 | Enablement session | TSE | Harold Moore (DC) | Not started |  |  | N
FIS Global | V3 | Retro within 48 hours | TSE | Harold Moore (DC) | Not started |  |  | Y
FIS Global | V4 | CS handover | TSE | Harold Moore (DC) | Not started |  |  | Y
Fidelity | P1 | Onboarding Record created and linked | TSE | Ravi Badana | Not started |  |  | Y
Fidelity | P2 | Technical assessment | TSE | Ravi Badana | Not started |  |  | Y
Fidelity | P3 | Permission pre-flight on named admins | TSE | Ravi Badana | Not started |  |  | Y
Fidelity | P4 | Engineering review; pre-facto noise suppression | Named engineer | OAE - FnF - Tracker | Not started |  |  | Y
Fidelity | P5 | Branch decisions recorded | TSE | Ravi Badana | Not started |  |  | Y
Fidelity | P6 | Wizard and branches workshop (TSE, TPE, PS) | TSE | Ravi Badana | Not started |  |  | N
Fidelity | P7 | Customer briefing: findings vs. issues, no template edits | PS | Stephen Lovett | Not started |  |  | N
Fidelity | P8 | Go / No Go with committed date | TSE + PS | Ravi Badana / Stephen Lovett | Not started |  |  | Y
Fidelity | D1 | First account validated end to end | PS | Stephen Lovett | Not started |  |  | Y
Fidelity | D2 | Named engineer on the call | Named engineer | OAE - FnF - Tracker | Not started |  |  | N
Fidelity | D3 | Deviations logged live | PS | Stephen Lovett | Not started |  |  | N
Fidelity | D4 | Org onboarded; Terraform applied | PS | Stephen Lovett | Not started |  |  | N
Fidelity | V1 | Validation: all scanners returning data | TSE + PS | Ravi Badana / Stephen Lovett | Not started |  |  | Y
Fidelity | V2 | Enablement session | TSE | Ravi Badana | Not started |  |  | N
Fidelity | V3 | Retro within 48 hours | TSE | Ravi Badana | Not started |  |  | Y
Fidelity | V4 | CS handover | TSE | Ravi Badana | Not started |  |  | Y
DOI | P1 | Onboarding Record created and linked | TSE |  | Not started |  |  | Y |  | Owner missing
DOI | P2 | Technical assessment | TSE |  | Not started |  |  | Y |  | Owner missing
DOI | P3 | Permission pre-flight on named admins | TSE |  | Not started |  |  | Y |  | Owner missing
DOI | P4 | Engineering review; pre-facto noise suppression | Named engineer | OAE - DOI - Tracker | Not started |  |  | Y
DOI | P5 | Branch decisions recorded | TSE |  | Not started |  |  | Y |  | Owner missing
DOI | P6 | Wizard and branches workshop (TSE, TPE, PS) | TSE |  | Not started |  |  | N |  | Owner missing
DOI | P7 | Customer briefing: findings vs. issues, no template edits | PS | Stephen Lovett | Not started |  |  | N
DOI | P8 | Go / No Go with committed date | TSE + PS | (no TSE) / Stephen Lovett | Not started |  |  | Y
DOI | D1 | First account validated end to end | PS | Stephen Lovett | Not started |  |  | Y
DOI | D2 | Named engineer on the call | Named engineer | OAE - DOI - Tracker | Not started |  |  | N
DOI | D3 | Deviations logged live | PS | Stephen Lovett | Not started |  |  | N
DOI | D4 | Org onboarded; Terraform applied | PS | Stephen Lovett | Not started |  |  | N
DOI | V1 | Validation: all scanners returning data | TSE + PS | (no TSE) / Stephen Lovett | Not started |  |  | Y
DOI | V2 | Enablement session | TSE |  | Not started |  |  | N |  | Owner missing
DOI | V3 | Retro within 48 hours | TSE |  | Not started |  |  | Y |  | Owner missing
DOI | V4 | CS handover | TSE |  | Not started |  |  | Y |  | Owner missing
Marriott | P1 | Onboarding Record created and linked | TSE | Khizar Karim | Not started |  |  | Y
Marriott | P2 | Technical assessment | TSE | Khizar Karim | Not started |  |  | Y
Marriott | P3 | Permission pre-flight on named admins | TSE | Khizar Karim | Not started |  |  | Y
Marriott | P4 | Engineering review; pre-facto noise suppression | Named engineer | OAE - Marriott - Tracker | Not started |  |  | Y
Marriott | P5 | Branch decisions recorded | TSE | Khizar Karim | Not started |  |  | Y
Marriott | P6 | Wizard and branches workshop (TSE, TPE, PS) | TSE | Khizar Karim | Not started |  |  | N
Marriott | P7 | Customer briefing: findings vs. issues, no template edits | PS | Bliss Jourdan | Not started |  |  | N
Marriott | P8 | Go / No Go with committed date | TSE + PS | Khizar Karim / Bliss Jourdan | Not started |  |  | Y
Marriott | D1 | First account validated end to end | PS | Bliss Jourdan | Not started |  |  | Y
Marriott | D2 | Named engineer on the call | Named engineer | OAE - Marriott - Tracker | Not started |  |  | N
Marriott | D3 | Deviations logged live | PS | Bliss Jourdan | Not started |  |  | N
Marriott | D4 | Org onboarded; Terraform applied | PS | Bliss Jourdan | Not started |  |  | N
Marriott | V1 | Validation: all scanners returning data | TSE + PS | Khizar Karim / Bliss Jourdan | Not started |  |  | Y
Marriott | V2 | Enablement session | TSE | Khizar Karim | Not started |  |  | N
Marriott | V3 | Retro within 48 hours | TSE | Khizar Karim | Not started |  |  | Y
Marriott | V4 | CS handover | TSE | Khizar Karim | Not started |  |  | Y
Honeywell | P1 | Onboarding Record created and linked | TSE |  | In progress |  |  | Y |  | Owner missing
Honeywell | P2 | Technical assessment | TSE |  | Done | 2026-08-18 | https://docs.google.com/document/d/1erYNnpmSYybPaQ9FyD8uTRDJP-QtDkCkYi9FP-1wz6Y/edit?tab=t.4w05kogx4q1t | Y |  | Owner missing
Honeywell | P3 | Permission pre-flight on named admins | TSE |  | In progress |  |  | Y |  | Owner missing
Honeywell | P4 | Engineering review; pre-facto noise suppression | Named engineer |  | Not started |  |  | Y |  | Owner missing
Honeywell | P5 | Branch decisions recorded | TSE |  | Not started |  |  | Y |  | Owner missing
Honeywell | P6 | Wizard and branches workshop (TSE, TPE, PS) | TSE |  | Not started |  |  | N |  | Owner missing
Honeywell | P7 | Customer briefing: findings vs. issues, no template edits | PS |  | In progress |  |  | N |  | Owner missing
Honeywell | P8 | Go / No Go with committed date | TSE + PS |  | Not started |  |  | Y |  | Owner missing
Honeywell | D1 | First account validated end to end | PS |  | Done | 2026-09-24 | AWS Org Onboarding Review | Y | Discovery Engine Errors, but High Coverage | Owner missing
Honeywell | D2 | Named engineer on the call | Named engineer |  | Not started |  |  | N |  | Owner missing
Honeywell | D3 | Deviations logged live | PS |  | Not started |  |  | N |  | Owner missing
Honeywell | D4 | Org onboarded; Terraform applied | PS |  | In progress |  |  | N |  | Owner missing
Honeywell | V1 | Validation: all scanners returning data | TSE + PS |  | Not started |  |  | Y |  | Owner missing
Honeywell | V2 | Enablement session | TSE |  | Not started |  |  | N |  | Owner missing
Honeywell | V3 | Retro within 48 hours | TSE |  | Not started |  |  | Y |  | Owner missing
Honeywell | V4 | CS handover | TSE |  | Not started |  |  | Y |  | Owner missing
Salesforce - ESS org | P1 | Onboarding Record created and linked | TSE | Khizar Karim | Not started |  |  | Y
Salesforce - ESS org | P2 | Technical assessment | TSE | Khizar Karim | Not started |  |  | Y
Salesforce - ESS org | P3 | Permission pre-flight on named admins | TSE | Khizar Karim | Not started |  |  | Y
Salesforce - ESS org | P4 | Engineering review; pre-facto noise suppression | Named engineer |  | Not started |  |  | Y |  | Owner missing
Salesforce - ESS org | P5 | Branch decisions recorded | TSE | Khizar Karim | Not started |  |  | Y
Salesforce - ESS org | P6 | Wizard and branches workshop (TSE, TPE, PS) | TSE | Khizar Karim | Not started |  |  | N
Salesforce - ESS org | P7 | Customer briefing: findings vs. issues, no template edits | PS | Bliss Jourdan | Not started |  |  | N
Salesforce - ESS org | P8 | Go / No Go with committed date | TSE + PS | Khizar Karim / Bliss Jourdan | Not started |  |  | Y
Salesforce - ESS org | D1 | First account validated end to end | PS | Bliss Jourdan | Not started |  |  | Y
Salesforce - ESS org | D2 | Named engineer on the call | Named engineer |  | Not started |  |  | N |  | Owner missing
Salesforce - ESS org | D3 | Deviations logged live | PS | Bliss Jourdan | Not started |  |  | N
Salesforce - ESS org | D4 | Org onboarded; Terraform applied | PS | Bliss Jourdan | Not started |  |  | N
Salesforce - ESS org | V1 | Validation: all scanners returning data | TSE + PS | Khizar Karim / Bliss Jourdan | Not started |  |  | Y
Salesforce - ESS org | V2 | Enablement session | TSE | Khizar Karim | Not started |  |  | N
Salesforce - ESS org | V3 | Retro within 48 hours | TSE | Khizar Karim | Not started |  |  | Y
Salesforce - ESS org | V4 | CS handover | TSE | Khizar Karim | Not started |  |  | Y
Matercard | P1 | Onboarding Record created and linked | TSE |  | Not started |  |  | Y |  | Owner missing
Matercard | P2 | Technical assessment | TSE |  | Not started |  |  | Y |  | Owner missing
Matercard | P3 | Permission pre-flight on named admins | TSE |  | Not started |  |  | Y |  | Owner missing
Matercard | P4 | Engineering review; pre-facto noise suppression | Named engineer |  | Not started |  |  | Y |  | Owner missing
Matercard | P5 | Branch decisions recorded | TSE |  | Not started |  |  | Y |  | Owner missing
Matercard | P6 | Wizard and branches workshop (TSE, TPE, PS) | TSE |  | Not started |  |  | N |  | Owner missing
Matercard | P7 | Customer briefing: findings vs. issues, no template edits | PS |  | Not started |  |  | N |  | Owner missing
Matercard | P8 | Go / No Go with committed date | TSE + PS |  | Not started |  |  | Y |  | Owner missing
Matercard | D1 | First account validated end to end | PS |  | Not started |  |  | Y |  | Owner missing
Matercard | D2 | Named engineer on the call | Named engineer |  | Not started |  |  | N |  | Owner missing
Matercard | D3 | Deviations logged live | PS |  | Not started |  |  | N |  | Owner missing
Matercard | D4 | Org onboarded; Terraform applied | PS |  | Not started |  |  | N |  | Owner missing
Matercard | V1 | Validation: all scanners returning data | TSE + PS |  | Not started |  |  | Y |  | Owner missing
Matercard | V2 | Enablement session | TSE |  | Not started |  |  | N |  | Owner missing
Matercard | V3 | Retro within 48 hours | TSE |  | Not started |  |  | Y |  | Owner missing
Matercard | V4 | CS handover | TSE |  | Not started |  |  | Y |  | Owner missing
Thales | P1 | Onboarding Record created and linked | TSE | Steve Briand | Not started |  |  | Y
Thales | P2 | Technical assessment | TSE | Steve Briand | Not started |  |  | Y
Thales | P3 | Permission pre-flight on named admins | TSE | Steve Briand | Not started |  |  | Y
Thales | P4 | Engineering review; pre-facto noise suppression | Named engineer |  | Not started |  |  | Y |  | Owner missing
Thales | P5 | Branch decisions recorded | TSE | Steve Briand | Not started |  |  | Y
Thales | P6 | Wizard and branches workshop (TSE, TPE, PS) | TSE | Steve Briand | Not started |  |  | N
Thales | P7 | Customer briefing: findings vs. issues, no template edits | PS | Ariel Nin | Not started |  |  | N
Thales | P8 | Go / No Go with committed date | TSE + PS | Steve Briand / Ariel Nin | Not started |  |  | Y
Thales | D1 | First account validated end to end | PS | Ariel Nin | Not started |  |  | Y
Thales | D2 | Named engineer on the call | Named engineer |  | Not started |  |  | N |  | Owner missing
Thales | D3 | Deviations logged live | PS | Ariel Nin | Not started |  |  | N
Thales | D4 | Org onboarded; Terraform applied | PS | Ariel Nin | Not started |  |  | N
Thales | V1 | Validation: all scanners returning data | TSE + PS | Steve Briand / Ariel Nin | Not started |  |  | Y
Thales | V2 | Enablement session | TSE | Steve Briand | Not started |  |  | N
Thales | V3 | Retro within 48 hours | TSE | Steve Briand | Not started |  |  | Y
Thales | V4 | CS handover | TSE | Steve Briand | Not started |  |  | Y
Gap Inc | P1 | Onboarding Record created and linked | TSE | Z Yu | Not started |  |  | Y
Gap Inc | P2 | Technical assessment | TSE | Z Yu | Not started |  |  | Y
Gap Inc | P3 | Permission pre-flight on named admins | TSE | Z Yu | Not started |  |  | Y
Gap Inc | P4 | Engineering review; pre-facto noise suppression | Named engineer | Z Yu | Not started |  |  | Y
Gap Inc | P5 | Branch decisions recorded | TSE | Z Yu | Not started |  |  | Y
Gap Inc | P6 | Wizard and branches workshop (TSE, TPE, PS) | TSE | Z Yu | Not started |  |  | N
Gap Inc | P7 | Customer briefing: findings vs. issues, no template edits | PS | Z Yu | Not started |  |  | N
Gap Inc | P8 | Go / No Go with committed date | TSE + PS | Z Yu | Not started |  |  | Y
Gap Inc | D1 | First account validated end to end | PS | Z Yu | Not started |  |  | Y
Gap Inc | D2 | Named engineer on the call | Named engineer | Z Yu | Not started |  |  | N
Gap Inc | D3 | Deviations logged live | PS | Z Yu | Not started |  |  | N
Gap Inc | D4 | Org onboarded; Terraform applied | PS | Z Yu | Not started |  |  | N
Gap Inc | V1 | Validation: all scanners returning data | TSE + PS | Z Yu | Not started |  |  | Y
Gap Inc | V2 | Enablement session | TSE | Z Yu | Not started |  |  | N
Gap Inc | V3 | Retro within 48 hours | TSE | Z Yu | Not started |  |  | Y
Gap Inc | V4 | CS handover | TSE | Z Yu | Not started |  |  | Y
Early Warning Services LLC | P1 | Onboarding Record created and linked | TSE | Lindsey Smith | Not started |  |  | Y
Early Warning Services LLC | P2 | Technical assessment | TSE | Lindsey Smith | Not started |  |  | Y
Early Warning Services LLC | P3 | Permission pre-flight on named admins | TSE | Lindsey Smith | Not started |  |  | Y
Early Warning Services LLC | P4 | Engineering review; pre-facto noise suppression | Named engineer |  | Not started |  |  | Y |  | Owner missing
Early Warning Services LLC | P5 | Branch decisions recorded | TSE | Lindsey Smith | Not started |  |  | Y
Early Warning Services LLC | P6 | Wizard and branches workshop (TSE, TPE, PS) | TSE | Lindsey Smith | Not started |  |  | Y
Early Warning Services LLC | P7 | Customer briefing: findings vs. issues, no template edits | PS |  | Not started |  |  | Y |  | Owner missing
Early Warning Services LLC | P8 | Go / No Go with committed date | TSE + PS | Lindsey Smith / (no PS) | Not started |  |  | Y
Early Warning Services LLC | D1 | First account validated end to end | PS |  | Not started |  |  | Y |  | Owner missing
Early Warning Services LLC | D2 | Named engineer on the call | Named engineer |  | Not started |  |  | Y |  | Owner missing
Early Warning Services LLC | D3 | Deviations logged live | PS |  | Not started |  |  | Y |  | Owner missing
Early Warning Services LLC | D4 | Org onboarded; Terraform applied | PS |  | Not started |  |  | Y |  | Owner missing
Early Warning Services LLC | V1 | Validation: all scanners returning data | TSE + PS | Lindsey Smith / (no PS) | Not started |  |  | Y
Early Warning Services LLC | V2 | Enablement session | TSE | Lindsey Smith | Not started |  |  | Y
Early Warning Services LLC | V3 | Retro within 48 hours | TSE | Lindsey Smith | Not started |  |  | Y
Early Warning Services LLC | V4 | CS handover | TSE | Lindsey Smith | Not started |  |  | Y
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing
[5 empty] | Not started |  |  | Y |  | Owner missing

## Deviations
Date | Account | Step ID | Cloud | What happened | Type | TAC / XSUP case # | Case tagged to upgrade at open? | Owner | Status | Feeds | Resolution / change landed